## Community Facilities
Community Facilities
Activity | Years | Responsible Party | Cost Estimate | Funding Source
Construct, as part of the Alpharetta City Center Redevelopment Project, a new City Hall to enhance ease of public access to government. See related items under the Economic Development and Natural and Historic Resources components. | 2008, 2009, 2010 | Community Develoment Department, Private Sector | $12 million | City of Alpharetta
Expand the Community Policing Program to continue meeting the City's level of service of 2.6 sworn officers per 1,000 residents | 2008, 2009, 2010, 2011 | Police Department | 200000 | Federal grants, City of Alpharetta
Continue expansion of the City's Greenway Program | 2008, 2009, 2010, 2011 | Recreation and Parks Department | $5 million | Impact Fees, City of Alpharetta
Develop the Encore Center for the Arts to include a 12,000 seat amphitheater, a 2,000 seat multi-use performance hall, and a 500 seat black box theater | 2008, 2009, 2010, 2011,2012 | Community Development Department, Woodruff Arts Center (WAC) | $70 million | City of Alpharetta, Fulton County, Woodruff Arts Center (WAC), Amphitheater revenues
Develop a veterans and public safety personnel memorial park at the corner of Westside Parkway and Old Milton Parkway on the grounds of Police Headquarters | 2008 | Community Development Department, Engineering / Public Works Department | 75000 | City of Alpharetta
Installation of air conditioning and other improvements to the Will Park gym | 2008 | Recreation and Parks Department | 76300 | City of Alpharetta
Construct a greenway trail to enhance pedestrian connectivity between Wills Park and the Downtown core | 2008, 2009, 2010 | Public Works Department, Community Development Department | $2 million | GO Bond Funds, Impact Fees, TE Funds
Construct the northern expansion of the Big Creek Greenway | 2008, 2009, 2010, 2011 | Public Works Department, Recreation and Parks Department | $2 million | GO Bond Funds, Impact Fees
Expand the Senior Activity Center | 2009, 2010 | Recreation and Parks Department, Engineering / Public Works Department | 200000 | City of Alpharetta, CDBG Funds
Alpharetta Community Center Phase III | 2009, 2010, 2011 | Recreation and Parks Department, Engineering / Public Works Department | 5000000 | City of Alpharetta
Expand the City's internal fiber optic and wireless networks | 2008, 2009, 2010, 2011, 2012 | Department of Information Technology | 700000 | City of Alpharetta
Construction and Implementation of Data Center / Network | 2008, 2009 | Department of Information Technology | 500000 | City of Alpharetta
Telephony Voice Over IP (VOIP) | 2010, 2011 | Department of Information Technology | 300000 | City of Alpharetta

## Economic Development
Economic Development
Activity | Years | Responsible Party | Cost Estimate | Funding Source
Through regular public meetings, complete annual updates to the Downtown Development Plan to ensure consistency of the plan with community needs and goals | 2008, 2009, 2010, 2011, 2012 | Community Development Department | 1000 | City of Alpharetta
Leverage City-owned property in the Downtown core to advance the adopted Downtown Plan through development of a mixed-use complex that features expanded City offices, public greenspace, and private retail, office, and residential uses (Alpharetta City Center). | 2008, 2009,2010, 2011 | Community Development Department, private sector | $96 million | Public / private partnership, Tax Allocation District
Update the City's economic development action plan to ensure consistency with overall community objectives and needs | 2008, 2009 | Community Development Department, Alpharetta Development Authority | $40, 300 | City of Alpharetta
Coordinate a technology forum to encourage an environment of innovation, build linkages between technology companies with a presence in the community, and attract new technology firms | 2008, 2009, 2010, 2011, 2012 | Community Development Department, Greater North Fulton Chamber of Commerce, private sector | $7,000 annually | Participants, private donations

## Transportation
Transportation
Activity | Years | Responsible Party | Cost Estimate | Funding Source
Intersection Improvements
Mayfield Road @ Canton Street | 2008, 2009 | Engineering / Public Works Department | 500000 | GO Bond Funds, Impact Fees, City of Alpharetta, Grants
Hembree Road and Maxwell Road | 2008, 2009 | Engineering / Public Works Department | 1200000 | GO Bond Funds, Impact Fees, City of Alpharetta, Grants, North Fulton CID
Kimball Bridge Road @ Waters Road | 2008, 2009 | Engineering / Public Works Department | 1200000 | GO Bond Funds, Impact Fees, City of Alpharetta, GDOT
Webb Bridge Road @Park Bridge/Shirley Bridge | 2008, 2009 | Engineering / Public Works Department | 1200000 | GO Bond Funds, Impact Fees, City of Alpharetta, GDOT
Old Milton Parkway @ North Point Pkwy. | 2008, 2009, 2010 | Engineering / Public Works Department / GDOT | 2000000 | GO Bond, GDOT
Kimball Bridge Road @ North Point Pkwy. | 2008, 2009 | Engineering / Public Works Department | 1200000 | City of Alpharetta, Impact Fees
Hwy. 9 @ Vaughn | 2008, 2009 | Engineering / Public Works Department | 1000000 | City of Alpharetta, Impact Fees, GO Bonds
Windward Pkwy. @North Point Pkwy. | 2008, 2009 | Engineering / Public Works Department | 500000 | City of Alpharetta, Impact Fees
Roads and Right-of-Way
Kimball Bridge Road and Bridge over Big Creek | 2008, 2009, 2010 | Engineering / Public Works Department | 500000 | GO Bonds, Impact Fees, City of Alpharetta, GDOT
Downtown connector road between Old Milton Parkway and Milton Avenue | 2008, 2009, 2010 | Engineering / Public Works Department | 3500000 | GO Bonds, Impact Fees, City of Alpharetta, Grants
Downtown alley project | 2007, 2008, 2009 | Engineering / Public Works Department | 300000 | GO Bonds, Impact Fees, City of Alpharetta, Grants
Sidewalks
Bethany Road | 2012, | Engineering / Public Works Department | 108000 | GO Bonds
Devore Road | 2012, | Engineering / Public Works Department | 219000 | GO Bonds, Impact Fees
Mid-Broadwell Road | 2008, 2009, 2010, 2011, 2012 | Engineering / Public Works Department | 748000 | GO Bonds
Other
Traffic Signal Interconnect | 2007, 2008, 2009, 2010, 2011, 2012 | Engineering / Public Works Department | 500000 | GO Bonds, Impact Fees, City of Alpharetta, Grants
Traffic Control Center | 2007, 2008, 2009, 2010, 2011, 2012 | Engineering / Public Works Department | 500000 | GO Bonds, Impact Fees, City of Alpharetta, Grants

## Housing
Housing
Activity | Years | Responsible Party | Cost Estimate | Funding Source
Encourage development, through a public / private venture, for the incorporation of housing in the Downtown Area | 2008, 2009, 2010, 2011, 2012 | Community Development Department | N/A | N/A
Encourage the development of a wide variety of housing types to accomopdate diverse ages and income levels. | 2008, 2009, 2010, 2011, 2012 | Community Development Department | N/A | N/A
Encourage development of housing opportunities for seniors that accomodates the needs of the aging population. | 2008, 2009, 2010, 2011, 2012 | Community Development Department | N/A | N/A
Encourage and promote higher density residential development along transportation corridors. | 2008, 2009, 2010, 2011,2012 | Community Development Department | N/A | N/A

## Land Use
Land Use
Activity | Years | Responsible Party | Cost Estimate | Funding Source
Continue application of the Cost of Government Services Land Use Model to forecast fiscal impacts of land use decisions within the City | 2008, 2009, 2010, 2011, 2012 | Community Development Department | N/A | N/A
Continue integration of the City's land use and transportation plans | 2008, 2009, 2010, 2011, 2012 | Community Development Department, Engineering / Public Works Department | N/A | N/A
Pursue annexation of the remaining unincorporated islands that currently exist within the main boundaries of the City of Alpharetta and between the boundaries of the City and surrounding jurisdictions, to which we currently provide services | Complete | Community Development Department, Finance Department, Engineering / Public Works Department | N/A | N/A

## Natural and Historic Resources
Natural And Historic Resources
Activity | Years | Responsible Party | Cost Estimate | Funding Source
Promote environmental awareness among the general public and the development community through educational programs | 2008, 2009, 2010, 2011, 2012 | Engineering / Public Works Department | 8000 | City of Alpharetta
Study applicability of incentives such as the transfer of development rights or tax abatements to encourage preservation of greenspace | 2008, 2009 | Engineering / Public Works Department, Community Development Department | N/A | N/A
Park land acquisition | 2008, 2009, 2010, 2011, 2012 | Recreation and Parks Department | 5000000 | GO Bond Funds, Impact Fees, Grants
As part of the construction of the new City Hall, develop a facility for the preservation and display of local historic documents and artifacts. | 2009, 2010 | Community Development Department | Included in City Hall construction cost | City of Alpharetta

## Other Considerations
Other Considerations
Activity | Years | Responsible Party | Cost Estimate | Funding Source
Install tornado alert sirens in newly annexed portions of the City | 2008, 2009 | Public Safety | 57000 | City of Alpharetta
To enhance public safety and improve traffic movement through the City, install red light cameras at "high incident" intersections | 2008, 2009, 2010, 2011, 2012 | Police Department | 300000 | City of Alpharetta, grant funds
Expand the City's Geographic Information System (GIS) capabilities and systems | 2008, 2009, 2010, 2011, 2012 | Technology Services | 70000 | City of Alpharetta

## General Planning
General Planning
Activity | Years | Responsible Party | Cost Estimate | Funding Source
Update and expand the computerized system for maintaining land development records, building permits, and engineering plans | 2008, 2009 | Department of Information Technology, Engineering / Public Works Department, Community Development Department | 25000 | City of Alpharetta
Update and expand the City's GIS capabilities and systems | 2009, 2010, 2011, 2012, | Department of Information Technology | 500000 | City of Alpharetta, Grants
Revise the Capital Improvements Plan annually as part of the budget process | 2008, 2009, 2010, 2011, 2012 | Finance Department | N/A | N/A
Develop a records management system for city-wide document storage | 2008, 2009, 2010, 2011, 2012 | Department of Information Technology, Finance | 350000 | City of Alpharetta, Grants