## Community Facilities
Community Facilities
Activity | Status | Explanation
Develop a Downtown Incentive Zoning Package to encourage development within the identified Downtown Plan Area that encourages mixed-use development with an emphasis on increasing residential options, and promotes a pedestrian oriented environment within the context of appropriate, historically sensitive architectural themes | Complete | N/A
Build a fire station at Windward Parkway and Highway 9 | Discontinued | Growth and development in the area made construction of a fire station on Kimball Bridge Road a higher priority in order to maintain appropriate levels of service. Further, the establishment of the new City of Milton along Alpharetta's northern boundaries precludes substantial growth in service need in the area that such a station would have served.
Continuie to improve training and responsiveness of the Fire Department | Underway | N/A
Become a "storm ready" city | Underway | N/A
Construct a new fire station on Kimball Bridge Road. | Completed | N/A
Continue to purchase acreage to maintain the City's 9.5 acres / 1,000 residents ratio | Ongoing
To enhance ease of public access to government, consolidate most City offices to City-owned property in the Downtown core as part of the overall mixed-use development of the site. | Underway | N/A
Construct a greenway trail to enhance pedestrian linkage between Wills Park and the Downtown core. | Underway | N/A
Construct an environmental education park adjacent to the Big Creek Greenway. | Underway | N/A
Construct a new playground facility at Cogburn Road Park. | Completed
Install air conditioning and other improvements to the Wills Park Gym. | Completed
Construct a Police evidence storage facility and garage. | Completed

## Economic Development
Economic Development
Activity | Status | Explanation
Via public input, create and adopt a new Downtown Development Plan that meets the standards of the Atlanta Regional Commission's Livable Centers Initiative | Complete | N/A
Leverage City-owned property for a development project that will serve as a catalyst to attract private investment and advance completion of the Downtown Development Plan. | Underway | N/A
Continue to place emphasis on enforcement of appropriate signage, landscaping and buffering controls | Underway | N/A
Identify and create an image or theme for selected areas of the City | Underway | N/A
Conduct an LCI study for the North Point Activity Center | Complete
Conduct a supplemental transportation study for Downtown Alpharetta | Complete

## Land Use
Land Use
Activity | Status | Explanation
Develop a Downtown Incentive Zoning Package to encourage development within the identified Downtown Plan Area that encourages mixed use development and promotes a pedestrian oriented environment within the context of appropriate, historically sensitive architectural themes. | Complete | N/A
Continue policies that interrelate land use and capital improvements planning. | Underway | N/A
Create a phased annexation plan that ensures surrounding unincorporated areas will be developed and/or maintained in a manner consistent with City land use policy and supportive of the health, welfare, and quality of life of Alpharetta residents. | Completed | N/A
Through annexation, provide sufficient land area within the City to accommodate appropriate residential and non-residential development. | Completed | N/A

## Natural and Historic Resources
Natural And Historic Resources
Activity | Status | Explanation
Continue the City's Operation Greenspace Program | Complete | N/A
Develop an Environmental Park that showcases native plant material and the natural environment | Complete
Restore the historic farm silos in the Crabapple area as a feature element in a new public park | Complete | N/A
Conduct a formal survey to identify all speciman trees within the Downtown Development Area. | Complete | N/A
Identify any land uses that pose a threat to valuable natural resources | Underway | N/A

## General Planning
General Planning
Activity | Status | Explanation
Work with Fulton County to identify growth areas and future school sites. | Completed | N/A
Implement the Comprehensive Plan to provide an aesthetically pleasing, pedestrian friendly and responsible environment | Underway | N/A
Update and expand the computerized system for maintaining land development records, building permits, and engineering drawings as data becomes available | Underway | N/A
Revise the Capital Improvements Plan annually as part of the budget process | Underway | N/A