## Housing
Fulton County Short Term Work Program
Short Term Work Program Update 2008-2012
Comprehensive Plan Element: | Housing
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Kensington Heights - Welcome All Road; 95 single family lots | 2005-02-01 | 2008-12-01 | 15200000 | Fulton County Housing and Community Development | HOME funds, Wachovia & Brand Banking Co. | CHDC loan=$384,300 for land acquisition provided inclusion of low to moderate income housing set aside. 98% complete
Ruby Creek - DeMooney Road; 25 single family lots | 2004-01-01 | 2009-04-01 | 5000000 | Fulton County Housing and Community Development | HOME funds, & Southern Community Bank | CHDC loan=$510,000 for land acquisition provided inclusion of low to moderate income housing set aside. In progress of infrastructure
Victoria Estates - Virlyn B. Smith Pkwy; older adult community, 27 single family homes | 2005-05-01 | 2009-06-01 | 4250000 | Fulton County Housing and Community Development | HOME funds & Southern Community Bank | CHDC loan=$340,000 for land acquisition provided inclusion of low to moderate income housing set aside. 5 houses built
Nelson McGee - Old National Hwy; 29-unit condominium for age 55 and older | 2004-10-01 | 2008-12-01 | 4950000 | Fulton County Housing and Community Development | HOME funds & BB & T. | CHDC loan=$399,000 for land acquisition and interest reserve account required by bank for infrastructure loan. Construction started
Harmony Village - Flat Shoals Road; 47-units | 2005-07-01 | 2008-12-01 | 7500000 | Fulton County Housing and Community Development | HOME funds & Flag Bank | FORECLOSED
Sweetwater Creek - a mixed income community with 34 single family homes | 2006-05-01 | 2008-12-01 | 7990000 | Fulton County Housing and Community Development | HOME Funds & private financing | CHDO Grant $525,000
Fulton County Housing Rehabilitation | 2008-01-01 | 2008-12-01 | 434217 | Fulton County Housing and Community Development | HOME Funds | 4 houses rehabilitated
Home Owner Assistance Program & American Dream | 2008-01-01 | 2008-12-01 | 575000 | Fulton County Housing and Community Development | HOME Funds & ADDI | Processed 68 loans and closed 55.
Walton Lakes - a 55+ Senior Community | 2008-03-01 | 2009-12-01 | 1500000 | Fulton County Housing and Community Development | HOME Funds
Washington Arms | 2008-03-01 | 2009-12-01 | 700000 | Fulton County Housing and Community Development | HOME Funds
Total Estimated Costs |  |  | 48099217

## Natural and Cultural Resources
Fulton County Short Term Work Program
Short Term Work Program Update 2008-2012
Comprehensive Plan Element: | Natural & Cultural Resources
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Review/approve EnvironmentalSite Analysis reports included in zoning applications | April 2008 | December 2012 | In-Kind | Environment and Community Development | Fulton County | Ongoing; Environmental Site Analysis report is required for all rezoning and use permit application
South Fulton Greenways Master Trail Plan (South Fulton TrailNet) | April 2008 | April 2009 | In-Kind | Environment and Community Development, Public Works | Fulton County | Ongoing; Develop a multi-use trail network that connects communities to schools, parks, community centers and commercial nodes via a pedestrian and bicycle network
Fulton Industrial Boulevard Redevelopment Project | April 2008 | April 2009 | In-Kind | Economic, Housing and Community Development, Environment and Community Development | Fulton County | Ongoing; Provide environmental expertise on redevelopment project
Green Team | April 2008 | December 2012 | In-Kind | Finance, Purchasing, General Services, Health & Wellness, Human Services, Personnel, Public Works, Public Affairs | Fulton County | Ongoing: Consolidated examination of County environmental policies and practices. Advancement of environmental goals within the County
Scrap Tire Amnesty | April 2008 | December 2012 | In-Kind | Health & Wellness, Public Works | Fulton County | Ongoing: Six locations for scrap tire disposal set up to decrease a mosquito species that breeds in tires and spreads West Nile Virus. Two permanent sites Merk Road and Morgan Falls. There is no charge to dispose the scrap tires. The tires will be processed by a local recycling facility.
Expand hazardous waste education program | April 2008 | April 2009 | In-Kind | Public Works | Fulton County | Ongoing
Sponsor a Hazardous Waste Amnesty Day | May 2008 | December 2009 | In-Kind | Public Works, Fire Department | Fulton County | Ongoing
Institute recycling program/education in South Fulton | May 2008 | December 2009 | In-Kind | Public Works, General Services | Fulton County | Ongoing
Seek WaterFirst designation with Georgia Department of Community Affairs | May 2008 | December 2009 | In-Kind | Public Works | Fulton County | Ongoing
Coordinate cleanup of Fulton Industrial corridor | May 2008 | December 2009 | In-Kind | Public Works, local businesses | Fulton County
Total Estimated Costs |  |  | 0

## Land Use
Fulton County Short Term Work Program
Short Term Work Program Update 2008-2012
Comprehensive Plan Element: | Land Use
Project/Activity Description | Estimated Project Start Date | Estimated Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Sandtown LCI Implementation | 2008-01-01 | 2008-12-01 | In-kind | Public Works | Fulton County/State/Federal
Old National LCI 5 Year Update | 2008-04-01 | 2008-09-01 | In-kind | Environment & Community Development | Fulton County
Amend all Overlay Districts in Zoning Resolution | 2008-01-01 | 2009-01-01 | In-kind | Environment & Community Development | Fulton County
Adopt Old National Streetscape Standards | 2008-02-01 | 2008-05-01 | In-kind | Environment & Community Development | Fulton County
Fulton Industrial Overlay District | 2009-01-01 | 2009-12-01 | In-kind | Environment & Community Development | Fulton County
Sign Amendments | 2008-02-01 | 2008-06-01 | In-kind | Environment & Community Development | Fulton County
Overlay District Boundary Resolution | 2008-03-01 | 2008-07-01 | In-kind | Environment & Community Development | Fulton County
Create Unified Development Ordinance | 2008-03-01 | 2009-01-01 | In-kind | Environment & Community Development | Fulton County
Annual Population Update | 2008-04-01 | 2008-10-01 | In-kind | Environment & Community Development | Fulton County
Amend 2025 Comprehensive Plan Policies | 2008-01-01 | 2009-12-01 | In-kind | Environment & Community Development | Fulton County
Cascade Palmetto Hwy & Campbellton- Fairburn Rd Intersection | 2007-08-01 | 2008-04-01 | In-kind | Environment & Community Development | Fulton County
Retail - Industrial Land Use Policies | 2008-04-01 | 2008-12-01 | In-kind | Environment & Community Development | Fulton County
Land Use Map Amendment | 2008-04-02 | 2008-12-02 | In-kind | Environment & Community Development | Fulton County
Amend Southwest and South Fulton Map | 2008-01-01 | 2008-12-02 | In-kind | Environment & Community Development | Fulton County
2030 Comprehensive Plan Update | 2010-01-01 | 2011-10-01 | In-kind | Environment & Community Development | Fulton County
Total Estimated Costs |  |  | 0

## Economic Development
Fulton County Short Term Work Program
Short Term Work Program Update 2008-2012
Comprehensive Plan Element: | Economic Development
Project/Activity Description | Estimated Project Start Date | Estimated Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Fulton County Business Improvement Loan Program (BILP) | 2005-01-01 | 2008-12-01 | 400000 | County Manager | CDBG | Underway
Women's Economic Development Agency | 2005-01-01 | 2008-12-01 | 13000 | County Manager | CDBG | Completed
Godby Road Business Park (Phase 1) | 2005-01-01 | 2010-12-01 | 100000000 | County Manager | Bonding Financing | Under Construction
South Fulton Technology Park Expansion | 2007-06-01 | 2010-12-01 | 30000000 | County Manager | Private Investment Corporation | Site Location Change
Sembler Company | 2005-01-01 | 2011-12-01 | 115000000 | County Manager | Bonding Financing | Under Construction
South Fulton Office Development | 2008-06-01 | 2012-12-01 | 10000000 | County Manager | Private Investment Syndication | Expansion Project
Premier South Entertainment (Phase 1) | 2008-03-01 | 2013-12-01 | 500000000 | County Manager | Private Investor & Bond Financing | Securing Investor Agreements
Manufacturing Plant | 2007-10-01 | 2010-10-01 | 24000000 | County Manager | Bonding Financing | Securing Financing
Professional Services Building | 2008-04-01 | 2010-07-01 | 7000000 | County Manager | Pension Funds | Securing Tenant Leases
Two Glenlake LLC | 2005-01-01 | 2010-12-01 | 120000000 | County Manager | Bonding Financing | Under Construction
Commercial Mixed-Use Project | 2007-04-01 | 2010-12-01 | 18000000 | County Manager | HOME Program | Securing Financing
Sherwood Development | 2009-01-01 | 2011-12-01 | 15000000 | County Manager | Private Equity Group | Re-Zoning Approval Process
B & B Development | 2007-11-01 | 2011-12-01 | 31000000 | County Manager | IPO & Private Equity Group | Acquiring Property and Re-zoning Process
Gateway Village | 2008-04-01 | 2010-07-01 | 28000000 | County Manager | Pension Funds | Pending Zoning Approval
Total Estimated Costs |  |  | 998413000

## Transportation
Fulton County Short Term Work Program
Short Term Work Program Update 2008-2012
Comprehensive Plan Element: | Transportation
Project Name | Type of Project | Estimated Project Start Date | Estimated Project End Date | Project/ Activity Estimated Cost | Responsible Department/Agency | Funding | Status/ Remarks | Districts
T009 Fairburn Road - Phase I | Upgrade | 1998-06-01 | 2011-01-30 | 1180033 | Fulton County | GDOT/Fulton County | Design Completed | District 7
T040 Cochran Mill Road over Pea Creek | Bridge Replacement | 2004-06-01 | 2008-05-10 | 886000 | Fulton County | GDOT/Fulton County | RFP | District 7
T114 SR 70/Fulton Industrial Boulevard | Widening | 1992-12-01 | 2008-12-31 | 29224060 | GDOT | GDOT/Fulton County | Construction | District 5
T123 Will Lee Road | Sidewalk/Bicycle Route | 2003-07-01 | 2009-08-09 | 2867714 | Fulton County | GDOT/Fulton County | Pre-Construction | District 7
T162 Sandtown Pedestrian Network | Sidewalk Improvement | 2005-06-01 | 2010-07-01 | 9774350 | Fulton County | GDOT/Fulton County | Design | District 7
T184 Off System Safety Pilot Project | Pedestrian Improvement | 2005-10-06 | 2008-12-08 | 279639 | Fulton County | GDOT/Fulton County | Pre-Construction | District 7
T185 Cascade-Palmetto Road (SR 70) over Deep Creek | Bridge Replacement | 2005-06-01 | 2008-10-08 | 3371200 | Fulton County / GDOT | GDOT/Fulton County | Construction | District 7
T186 Cascade-Palmetto Road (SR 154) over Bear Creek | Bridge Replacement | 2005-06-01 | 2010-04-01 | 2193954 | Fulton County / GDOT | GDOT/Fulton County | Design | District 7
T188 Buffington Road - Phase II | Upgrade | 2005-09-01 | 2011-02-01 | 3494890 | Fulton County | GDOT/Fulton County | Design | District 7
T193 Fairburn Road - Phase II | Road Upgrade Improvement | 1998-06-01 | 2011-12-01 | 2234911 | Fulton County | GDOT/Fulton County | Design Completed | District 7
T208 SR 154 (Cascade-Palmetto Hwy) at Wilkerson Mill Road | Intersection Improvement | 2007-07-30 | 2010-08-01 | 2190000 | GDOT | GDOT/Fulton County | RFP | District 7
T209 SR 279 (Old National Hwy) Transit-Oriented Development | Sidewalk Improvement | 2007-07-30 | 2010-11-01 | 1650000 | Fulton County / College Park | GDOT/Fulton County | RFP | District 7
T210 SR 14 (South Fulton Parkway) Access Management Plan | Study | 2007-07-30 | 2010-12-12 | 400000 | Fulton County / GDOT | GDOT/Fulton County | RFP | District 7
T211 SR 279 (Old National Highway) ATMS | Arterial Communication | 2007-07-30 | 2011-01-01 | 800000 | Fulton County / GDOT | GDOT/Fulton County | RFP | District 7
T212 Oakley Industrial Boulevard | Road Upgrade Improvement | 2005-09-01 | 2011-11-01 | 6858212 | Fulton County | GDOT/Fulton County | Design | District 7
T213 SR 154 (Cascade-Palmetto Hwy) at Cedar Grove Road/Ridge Road | Intersection Improvement | 2005-12-01 | 2009-10-01 | 1480000 | GDOT | GDOT/Fulton County | RFP | District 7
T227 Butner Road over Camp Creek | Bridge Improvement | 2008-04-07 | 2010-10-25 | 1800000 | Fulton County | GDOT/Fulton County | RFP | 7
T237 Cascade-Palmetto Hwy (SR70) over Camp Creek | Bridge Replacement | 2001-03-05 | 2009-02-05 | 3242000 | GDOT | GDOT/Fulton County | Design | 7
T241 Bethsaida Road over Morning Creek Tributary | Bridge Improvement | 2006-09-05 | 2010-12-02 | 1710000 | Fulton County | Fulton County | Design | 7
T242 Butner Road at Stonewall Tell Road | Intersection Improvement | 2008-04-07 | 2011-01-19 | 2725000 | Fulton County | Fulton County | RFP | 7
T243 Reynolds Road at Westlake Parkway | Intersection Improvement | 2007-08-10 | 2008-12-11 | 315846 | Fulton County | Fulton County | Pre-Construction | 7
Total Estimated Costs |  |  |  | 78677809

## CIP - Wastewater
Fulton County Short Term Work Program
Short Term Work Program Update 2008-2012
2008 - 2012 WASTEWATER CIP PROJECTS
Project Number | Project Name | Estimated Cost | Contract Amount | Project Description | Source Document(s) | Authorized Date | PM Start Date | Construction Start | Construction Complete
S105 | Wastewater System Model & Comprehensive Master Plan | 2739913 |  | A detailed computer generated hydraulic model of the wastewater collection and conveyance system using information obtained from the Survey and Inventory project (S217). The purpose is to develop a comprehensive master plan outlining the capacity and maintenance needs of the wastewater system. |  |  |  | 2005-12-12 | 2009-06-04
S107 | CMMS / CIS Billing, Software/Hardware Procurement | 2587094 |  | Procurement of software and hardware in support of Project S106 |  |  |  | 2007-12-06 | 2009-03-19
S109 | Riverside Road Pump Station Upgrade | 13755321 |  | This project involves professional architectural and engineering design services for improving the various existing functions of the pump station including odor control and an increase in firm pumping capacity of the Pump Station from 40 Millions Gallons per Day (“MGD”) to 80 MGD. The design RFP also provides for the emergency power supply of three pump stations in North Fulton. |  |  |  | 2007-11-12 | 2009-12-15
S110 | Marsh Creek Sewer Upgrade | 3826000 |  | To clean and line 14,000 feet of sewer interceptor and trunk lines in the Marsh Creek Sewer Basin. Work involves lining of 8-inch, 12-inch, and 18-inch pipe, with 10-inch, 12-inch, 22-inch, 24-inch, and 28-inch HDPE and DIP. Rehabilitation of up to 60 manholes may be required. Design Ongoing |  |  |  | TBD | TBD
S115 | Johns Creek Environmental Campus | 134742941 |  | Relocation of the Johns Creek WTP to a new location on 43 acres of land bordered by Holcomb Bridge Rd and the Chattahoochee River in Northeast Fulton County. The facility will be expanded to 15 MGD capacity. The facility will use Membrane Bio-Reactor technology and will meet or exceed current advanced discharge limits and provide high quality urban reuse water to surrounding irrigation customers. |  |  |  | 2006-06-14 | 2009-12-09
S231 | Marsh Creek P.S. | 2307823 |  | Design & construct a new P.S to replace existing facility |  |  |  | 2009-03-09 | 2010-03-10
TOTAL 2008 - 2012 WASTEWATER PROJECTS |  | 159959092 | #REF!
Funding Source: Water & Sewerage Revenue Bonds Series

## CIP - Water
Fulton County Short Term Work Program
Short Term Work Program Update 2008-2012
2008-2012 WATER CIP PROJECTS
Project Number | Project Name | Estimated Cost | Contract Amount | Project Description | Source Document(s) | Authorized Date | PM Start Date | Construction Start | Construction Complete
W026 | North Fulton Maintenance & Operations Center | 8991083 |  | Design completed for the facility, but the construction of the North Fulton Maintenance & Operations Center on Maxwell Rd. in Alpharetta has been put on hold. | Fulton County Technical Services, July 2003. |  | 2004-05-03 | TBD | TBD
W027 | North Fulton Pump Stations | 635521 |  | Design of two booster pump stations to provide increased pressure and improved flow for the North Fulton Water System (W031, W032) Design Complete | Hydraulic Model Expansion and Calibration of the North Fulton County Water System, Metcalf & Eddy, Inc., August 2003. |  | 2005-08-15 | 2008-07-08 | 2009-07-20
W030 | Mansell Rd. Booster Pump Construction and Providence Rd. Booster Pump Construction | 2826140 |  | Construction of a 50 HP booster pump station at Mansell Road to provide increased pressure and improved flow for the North Fulton Water System and Construction of a 75 booster pump station at Providence and Cowart Roads to provide increased pressure and improved flow for the North Fulton Water System. |  |  |  | 2008-07-01 | 2009-07-20
W032 | Freemanville Rd. Elevated Storage Tank | 1594478 |  | Construction of a 0.50 MGD elevated storage tank at Freemanville Road near Henderson Road to provide increased pressure and improved flow for the North Fulton Water System. |  |  |  | 2008-06-01 | 2009-08-06
W032A | Pritchard Mountain Freemanville Rd. Water Main | 4165289 |  | Construction of approximately 30,000 linear feet of 24-inch diameter water main along Freemanville Road to the storage tanks at Freemanville Road near Henderson Road to provide increased pressure and improved flow for the North Fulton Water System. |  |  |  | 2007-09-01 | 2008-07-20
W035 | Riverside Road Water Main | 4542974 |  | Construction of approx. 10,800 LF of new water main, from 8-inch to 24-inch, along Riverside Dr between Atlanta Rd and GA-400 in the City of Roswell. |  |  |  | 2007-06-07 | 2008-10-08
W037 | Hackett Rd. North Fulton (West of GA-400) Storage Tanks | 5887486 |  | Construction of two 2-million gallon elevated storage tanks and related piping at a site in Northwest Roswell to improve fire protection supply. |  |  |  | 2007-10-07 | 2008-10-08
W038 | AFCWTP Phase 3.0 | 28000000 |  | Fulton County contribution to expansion of the Atlanta / Fulton County Water Treatment Plant. Design Ongoing |  |  |  | TBD | TBD
W039A | Alpharetta Water Transmission Main Design | 922173 |  | Design of approximately 24,000 ft of 54-inch water transmission main and 6,000 ft of 42-inch transmission main from the intersection of Buice Road and Jones Bridge Road to a point north west of downtown Alpharetta |  |  |  | TBD | TBD
W039B | Crabapple Road Water Main Design | 238257 |  | Design of approximately 12,000 feet of 16-inch water main beginning at the existing 24 inch line on Crossville Road (Hwy92) the run north approximately 10,000 feet along Crabapple Road to the existing 8-inch line on Hardscrabble Road. There will also be a 16-inch leg that tees off onto Hembree Road to the west for approximately 2000 linear feet to tie into the 16-inch line leading to the Hembree Road elevated tank |  |  |  | 2008-04-07 | 2010-04-07
W039C | Alpharetta Pipe Replacement Phase 2 | 2500000 |  | Replacement of asbestos-cement, galvanized, and PVC water pipe as well as other repairs and enhancements in excess of 40,000 feet for the Alpharetta water system. |  |  |  | TBD | TBD
TOTAL 2008 - 2012 WATER PROJECTS |  | 60303401 | 0

## Community Facilities
Fulton County Short Term Work Program
Short Term Work Program Update 2008-2012
Comprehensive Plan Element: | Community Facilties
Section: | Solid Waste
Project/Activity Description | Estimated Project Start Date | Estimated Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Update Solid Waste Plan | 2008-04-01 | 2008-10-01 | In-Kind | Public Works | Fulton County
Total Estimated Costs |  |  | 0
Comprehensive Plan Element: | Community Facilties
Section: | Public Facilities & Services
Project/Activity Description | Estimated Project Start Date | Estimated Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
North Fulton Charities (Facility Improvements) | 2008-01-01 | 2009-12-01 | 80000 | Fulton County | CDBG
Jefferon Place Career Center | 2009-01-01 | 2010-01-01 | 2700000 | Human Services | General Fund
Cliftondale School Renovation | 2008-06-01 | 2008-12-01 | 800000 | Arts Council | General Fund
10th Floor Waterproofing | 2008-06-01 | 2012-12-01 | 10000000 | General Service | General Fund
Fairburn Senior Center | 2006-04-01 | 2008-03-01 | 4784351 | Human Services | General Fund | Complete
Total Estimated Costs |  |  | 18364351
Comprehensive Plan Element: | Community Facilties
Section: | Public Safety Facilities & Services
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Fire Station 1 Renovation | 2009-01-01 | 2009-12-01 | 500000 | Fire Department | Capital
Fire Station 7 Renovation | 2009-01-01 | 2009-12-01 | 325000 | Fire Department | Capital
Fire Station 23 Waterproofing | 2008-08-01 | 2008-12-01 | 45000 | Fire Department | Capital
JCC Command Center and Security Systems | 2008-12-01 | 2009-12-01 | 4500000 | Sheriff Department | General Fund
JCT Security Modifications | 2008-06-01 | 2008-12-01 | 550000 | Sheriff Department | General Fund / USAI Grant
JCT Balcony Enclosure | 2009-01-01 | 2009-12-01 | 200000 | Juvenile Court | General Fund
Total Estimated Costs |  |  | 6120000
Comprehensive Plan Element: | Community Facilties
Section: | Recreational Facilities & Services
Project/Activity Description | Estimated Project Start Date | Estimated Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Southwest Arts Performance Theater | 2006-07-01 | 2008-09-01 | 8594025 | Arts Council | General Fund
Wolf Creek Amphitheater | 2007-10-01 | 2008-08-01 | 6100000 | Arts Council | General Fund
Welcome All Park indoor Renovation -Phase 1 | 2008-01-01 | 2008-08-01 | 80000 | Parks & Recreation | SSD | Remodel Kitchen; New Playground; Receptionist/Office area remodeling
Welcome All Park Major Pool Repair-Phase 2 | 2009-01-01 | 2009-12-01 | 206000 | Parks & Recreation | SSD | Replace Pool Pak (Dehumidifier)
Welcome All Park & Field upgrade - Phase 3 | 2010-01-01 | 2010-12-01 | 250000 | Parks & Recreation | SSD | New restrooms at field 4;Install water line to field 5;Connect to County wide pathway trail system; 2 additional shelters; Replace Concession Stand
Creel Park Renovation - Phase 1 | 2008-01-01 | 2008-12-01 | 30000 | Parks & Recreation | SSD | New flooring in multipurpose room & Kitchen; Replace carpet in lobby & offices; repaint interior and exterior columns: New reception Furniture; Window tints
Creel Park Parking Expansion - Phase 2 | 2012-01-01 | 2012-12-01 | 150000 | Parks & Recreation | SSD | Add 100 additional parking spaces
Cedar Grove Park upgrade - Phase 1 | 2008-01-01 | 2008-12-01 | 90000 | Parks & Recreation | SSD | Install 1/4 mile walking track; New Playground; Picnic Pavilion
Cedar Grove Park upgrade - Phase 2 | 2009-01-01 | 2009-12-01 | 200000 | Parks & Recreation | SSD | New Restroom; New Field Lights; Resurface Parking; Connect to Pathway Trail System.
Cedar Grove Community Building -Upgrade | 2008-08-01 | 2009-08-01 | 60000 | Parks & Recreation | SSD | Upgrade restrooms and parking to meet ADA Standards
Old National Park | 2008-01-01 | 2008-12-01 | 20000 | Parks & Recreation | SSD | Install new playground; Connect to Pathway Trail System
Beavers House Renovation - Phase 1 | 2009-01-01 | 2009-12-01 | 75000 | Parks & Recreation | SSD | Fill in existing pool; Build new gazebo and back deck; repair back porch.
Beavers House Renovation - Phase 2 | 2010-01-01 | 2010-12-01 | 60000 | Parks & Recreation | SSD | Kitchen Upgrade; bathroom upgrade; install new water well.
Burdette Park- Phase 1 | 2009-01-01 | 2009-12-01 | 75000 | Parks & Recreation | SSD | Build 1/4 mile walking track; Install new playground
Burdette Park- Phase 1 | 2011-01-01 | 2011-12-01 | 100000 | Parks & Recreation | SSD | New picnic shelter; Outdoor restrooms; Resurface Parking
Burdette Tennis Center-Phase 1 | 2009-01-01 | 2009-12-01 | 25000 | Parks & Recreation | SSD | New Light Fixtures; Paint interior and exterior
Burdette Tennis Center-Phase 2 | 2010-01-01 | 2010-12-01 | 40000 | Parks & Recreation | SSD | Resurface tennis courts
Cliftondale Recreation Facility-Phase 1 | 2008-01-01 | 2008-12-01 | 20000 | Parks & Recreation | SSD | Build two additional dug outs; New sign; Landscaping; Office remodeling; New Fencing
Cliftondale Recreation Facility-Phase 2 | 2009-01-01 | 2009-12-01 | 150000 | Parks & Recreation | SSD | New Concession Stand
Sandtown Ball Park | 2011-01-01 | 2011-12-01 | 150000 | Parks & Recreation | SSD | New Concession Stand
So. Fulton Tennis Center-Phase 1 | 2008-01-01 | 2008-12-01 | 30000 | Parks & Recreation | SSD | New Flooring in Ladies locker Room; Major Roofing repairs; New Windows installed
So. Fulton Tennis Center-Phase 2 | 2010-01-01 | 2010-01-01 | 80000 | Parks & Recreation | SSD | Repaving of Tennis Courts
Security Monitoring Improvements | 2008-01-01 | 2008-12-01 | 35000 | Parks & Recreation | SSD | Security Camera for 6 Facilities
Total Estimated Costs |  |  | 16620025
Comprehensive Plan Element: | Community Facilties
Section: | Hospitals & Other Public Health Facilities
Project/Activity Description | Estimated Project Start Date | Estimated Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Health Center Mechanical | 2008-04-01 | 2008-12-01 | 451000 | Health Department | General Fund
Total Estimated Costs |  |  | 451000
Comprehensive Plan Element: | Community Facilties
Section: | Libraries & Other Cultural Facilities
Project/Activity Description | Estimated Project Start Date | Estimated Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Alpharetta (New branch library) | 2009-09-01 | 2011-03-01 | 24732476 | Atlanta-Fulton Public Library | Bond Issue | Contingent upon issuance of bonds
Central (New Library) | TBD | TBD | 84807771 | Atlanta-Fulton Public Library | Bond Issue/Private | Contingent upon issuance of bonds and private funds totaling $82,942,107
East Roswell (New branch library) | 2009-09-01 | 2011-03-01 | 10900240 | Atlanta-Fulton Public Library | Bond Issue | Contingent upon issuance of bonds
Milton (New branch library) | 2009-09-01 | 2011-03-01 | 19129976 | Atlanta-Fulton Public Library | Bond Issue | Contingent upon issuance of bonds
Northwest Atlanta (New branch library) | 2009-09-01 | 2011-03-01 | 21132146 | Atlanta-Fulton Public Library | Bond Issue | Contingent upon issuance of bonds
Palmetto/Chattahoochee Hill Country (New branch library) | 2009-09-01 | 2011-03-01 | 7266827 | Atlanta-Fulton Public Library | Bond Issue | Contingent upon issuance of bonds
Southeast Atlanta (New branch library) | 2009-09-01 | 2011-03-01 | 10411662 | Atlanta-Fulton Public Library | Bond Issue | Contingent upon issuance of bonds
Stewart-Lakewood (New branch library) | 2009-09-01 | 2011-03-01 | 21449943 | Atlanta-Fulton Public Library | Bond Issue | Contingent upon issuance of bonds
Wolf Creek (New branch library) | 2009-09-01 | 2011-03-01 | 18167067 | Atlanta-Fulton Public Library | Bond Issue | Contingent upon issuance of bonds
Demolitions | 2009-09-01 | 2011-03-01 | 188882 | Atlanta-Fulton Public Library | Bond Issue | Contingent upon issuance of bonds
Auburn Avenue Research Library (Expansion) | 2009-09-01 | 2011-03-01 | 24996263 | Atlanta-Fulton Public Library | Bond Issue | Contingent upon issuance of bonds
South Fulton (Expansion) | 2009-09-01 | 2011-03-01 | 8416283 | Atlanta-Fulton Public Library | Bond Issue | Contingent upon issuance of bonds
Total Estimated Costs |  |  | 251599536