## 2001-2005 STWP
FY 2001-2005 STWP | ED=Economic Development, NH=Natural and Historic Resources, CFS=Community Facilities and Services, HS=Housing, LU=Land Use, AD=Administrative Work Item
SPLOST=Special Purpose Local-Option Sales Tax, Moreland-Altobelli=SPLOST Managers, CMAQ, Q023 = Federal Transportation Funds
General Funds=City general funds, operating revenue=city water/sewer operating funds, impact fees=water/sewer tap fees, GBT=Ben Turnipseed Engineers
HC-DOT=Henry County Department of Transportation, GaDOT=Georgia Department of Transportation, BOE=Board of Education
DCA=Department of Community Affiars, DNR=Department of Natural Resources, CDBG=Community Development Block Grant program
Project Name/Description | Plan Element | Local ID | ARC ID | Amount | FY 2001 | FY 2002 | FY 2003 | FY 2004 | FY 2005 | Start Year | Completion Year | Party Responsible | Funding Source
City of McDonough
Natural and Historic Resources
Maintain cultural and historical integrity of the Downtown Square | NH | MCNH001 |  | 0 | [5 empty] | 2000 | ongoing | City of McDonough, McDonough Business Association, Advancement in McDonough (AIM), University of Georgia | Private Funds
Prepare Stormwater Master Plan and Utility Program | NH | MCNH002 |  | 50000 | [5 empty] | 2000 | 2001, pending available funding | GBT Engineers, City of McDonough | general funds, operating revenues
Create Historic District | NH | MCNH003 |  | 10000 | [5 empty] | 2000 | completed 2000 | City of McDonough, Consultant, Historic Commission | general funds, grant
Initiate a program for homeowners and businesses who are interested in having their properties listed on Federal, State, and local historic registers | NH | MCNH004 |  | 5000 | [5 empty] | 2000 | 2002 | City of McDonough, Historic Commission | general and private funds
Maintain a registry of properties deemed historically significant for inclusion in Federal State, or local registers | NH | MCNH005 |  | 5000 | [5 empty] | 2000 | 2002 | City of McDonough, Consultant, Historic Commission | general funds, grant
Maintain a registry of properties deemed historically significant for inclusion in Federal State, or local registers | NH | MCNH006 |  | 5000 | [5 empty] | 2000 | 2002 | City of McDonough, Consultant, Historic Commission | general funds, grant
Improve substandard drainage systems throughout the City | NH | MCNH007 |  | 750000 | [5 empty] | 2000 | 2004 | City of McDonough, GBT Engineers, Allen-Smith Consulting | general funds, CDBG
Develop a Watershed Assessment and regulations for streams in the City | NH | MCNH008 |  | 30000 | [5 empty] | 2000 | 2004 | City of McDonough, GBT Engineers | general funds, operating revenues
Develop standards for Phase II of the NPDES Stormwater Program | NH | MCNH009 |  | 10000 | [5 empty] | 2000 | 2005 | City of McDonough, GBT Engineers | general funds, operating revenues
Economic Development
Prepare development guidelines for quality development to accommodate forecasted population increases | ED | MCED001 |  | 0 | [5 empty] | 2000 | 2002 | City of McDonough, McDonough Business Association, Advancement in McDonough (AIM), University of Georgia
Establish and maintain program to attract business and industry | ED | MCED002 |  | 0 | [5 empty] | 2001 | 2005 | City of McDonough
Prepare inentory of available land for suitable in-fill development | ED | MCED003 |  | 0 | [5 empty] | 2000 | 2002 | City, MBA
Work with local business leaders in the establishment of a Main Street program for the central city | ED | MCED004 |  | 50000 | [5 empty] | 2001 | 2002 | City, MBA, AIM | general and private funds
Capital Facilities and Services
General:
Complete new Capital Improvements Plan for Transportation, Recreation, and Public Safety | CFS | MCCFS001 |  | 10000 | [5 empty] | 2000 | ongoing | City of McDonough | general funds
Water and Sewer projects:
Analyze water system for leakage and pressure | CFS | MCCFS002 |  | 50000 | [5 empty] | 2000 | 2001 | City of McDonough, GBT Engineers | general funds, operating revenue
Prepare a Facilities Utilization Plan | CFS | MCCFS003 |  | 40000 | [5 empty] | 2000 | 2001 | City of McDonough, Consultant | general funds
Expand water and sewer systems, line extensions, various | CFS | MCCFS004 |  | 4200000 | [5 empty] | 2000 | 2005 | City of McDonough, Private Developers | operating funds, impact fees, private contributions
Enlarge Walnut Creek Wastewater Treatment Facility by 1.0 mgd | CFS | MCCFS005 |  | 6500000 | [5 empty] | 2000 | 2002 | GBT Engineers, City of McDonough | SPLOST, general funds, GEFA loans, impact fees
Study water infiltration of sanitary sewer systems | CFS | MCCFS006 |  | 100000 | [5 empty] | 2000 | 2005 | GBT Engineers, City of McDonough | general funds
Construct new water tank on West Side of the City at Kelly Road | CFS | MCCFS007 |  | 1000000 | [5 empty] | 1999 | 2000 | GBT Engineers, City of McDonough | general funds, impact fees
Evaluate future capacity of wastewater treatment facility | CFS | MCCFS008 |  | 20000 | [5 empty] | 1999 | 2001 | GBT Engineers, City of McDonough | general funds, operating revenue
Develop projections for future demands on water and sewer capacities | CFS | MCCFS009 |  | 20000 | [5 empty] | 1999 | ongoing | GBT Engineers, City of McDonough | general funds, operating revenue
Evaluate proportionate share impact fees | CFS | MCCFS010 |  | N/A | [5 empty] | 2000 | 2001 | GBT Engineers, City of McDonough | general funds, operating revenue
Fire and EMS projects:
Maintain fire fighting ability | CFS | MCCFS011 |  | 250000 | [5 empty] | 2001 | ongoing | City of McDonough Fire Department | general funds
Purchase of new ladder truck | CFS | MCCFS012 |  | 500000 | [5 empty] | 2002 | 2003 | City of McDonough Fire Department | general funds
New West Side Fire Station | CFS | MCCFS013 |  | 500000 | [5 empty] | 2002 | 2004 | City of McDonough Fire Department | general funds, private developer contribution
New Equipment for New West Side Station | CFS | MCCFS014 |  | 500000 | [5 empty] | 2003 | 2004 | City of McDonough Fire Department | general funds
Purchase of Ambulance | CFS | MCCFS015 |  | 100000 | [5 empty] | 2001 | 2003 | Henry County Fire Department | BOC general funds
Expansion/Renovation of Fire Station 1 | CFS | MCCFS016 |  | 350000 | [5 empty] | 2001 | 2003 | City of McDonough Fire Department | general funds
Transportation projects:
Thoroughfare Plan | CFS | MCCFS017 |  | 10000 | [5 empty] | 1999 | 2002 | City of McDonough | general funds
SR 42 N-S One-Way Pair System through Central McDonough: Racetrack to Carmichael Street | CFS | MCCFS018 | HE 010 | 2620000 | [5 empty] | 1999 | 2005 | GaDOT, HC-DOT, Moreland-Altobelli, City of McDonough | Federal Q023 funds, SPLOST, general funds, GaDOT contract funds
SR 20/81 E-W One-Way Pair System through Central McDonough: Jonesboro Rd, Keys Ferry Street | CFS | MCCFS019 | HE 008 | 2050000 | [5 empty] | 2000 | 2005 | GaDOT, HC-DOT, Moreland-Altobelli, City of McDonough | Federal Q023 funds, SPLOST, general funds, GaDOT contract funds
Bike Lanes along Pairs/Bryan Street | CFS | MCCFS020 | HE-AR | 450000 | [5 empty] | 2000 | 2003 | GaDOT, City of McDonough, Bron Cleveland & Associates | general funds, CMAQ funding
Road resurfacing as part of SPLOST | CFS | MCCFS021 |  | 3500000 | [5 empty] | 1999 | 2004 | Moreland-Altobelli, GaDOT, HC-DOT, City | GaDOT contract funds, general funds, SPLOST
SR 155 at Racetrack Road, CR 376 | CFS | MCCFS022 |  | 617000 | [5 empty] | 2000 | 2003 | Moreland-Altobelli, GaDOT, HC-DOT, City | GaDOT contract funds, general funds, SPLOST
Jonesboro Road Widening, I-75 to Southern RR in McDonough (2-4 divided median) | CFS | MCCFS023 | HE 007A | 12900000 | [5 empty] | 2000 | 2005 | Moreland-Altobelli, GaDOT, HC-DOT | GaDOT contract funds, general funds, SPLOST
Jonesboro Road at McDonough Pwy, Intersection improvement and Signalization | CFS | MCCFS024 |  | 440000 | [5 empty] | 2000 | 2001 | Moreland-Altobelli, GaDOT, HC-DOT, developer | GaDOT contract funds, general funds, SPLOST, private funds
Jonesboro Road at Kelly Road, Intersection improvement and Signalization | CFS | MCCFS025 |  | 360000 | [5 empty] | 2001 | 2003 | Moreland-Altobelli, GaDOT, HC-DOT, developer | GaDOT contract funds, general funds, SPLOST, private funds
Jonesboro Road at Dailey Mill and Wesley Lakes, Intersection improvement and Signalization | CFS | MCCFS026 |  | 360000 | [5 empty] | 2001 | 2003 | Moreland-Altobelli, GaDOT, HC-DOT, developer, City | GaDOT contract funds, general funds, SPLOST, private funds
Parks and Recreation projects:
Study local neighborhood park needs | CFS | MCCFS027 |  | 35000 | [5 empty] | 1999 | 2002 | Community Development, Parks, City | general funds
Prepare maintenance plan to address existing and future recreation needs | CFS | MCCFS028 |  | 0 | [5 empty] | 1999 | 2002 | Community Development, Parks, City | general funds
Prepare recycling plan | CFS | MCCFS029 |  | 0 | [5 empty] | 2002 | 2005 | City of McDonough | general funds, local assistance
Housing
Revise code enforcement ordinances and minimum housing standards | HS | MCHS001 |  | 5000 | [5 empty] | 2000 | completed | City of McDonough | general funds
Establish annual review system for identifying substandard housing units | HS | MCHS002 |  | 0 | [5 empty] | 2000 | 2004 | City fo McDonough
Initiate a study to determine the average single-family residence median value that represents a break-even point for services provided by the City | HS | MCHS003 |  | 10000 | [5 empty] | 2001 | 2002 | City fo McDonough | general funds
Revise zoning and development ordinances to provide for TND development and open spaces in new development | HS | MCHS004 |  | 5000 | [5 empty] | 2000 | 2002 | City of McDonough Community Development | general funds
Prepare new development guidelines and standards that will require sidewalks, pedestrian-scale lighting, landscaping, building standards, open spaces, and conservation easements | HS | MCHS005 |  | 10000 | [5 empty] | 2001 | 2002 | City of McDonough | general funds
Establish committee to prepare a study on Federal Housing developments to determine their visibility and needs | HS | MCHS006 |  | 0 | [5 empty] | 2001 | 2002 | City of McDonough | general funds
Initiate a market study and consumer satisfaction inquiry survey for establishing a plan to provide needed services such as affordable housing | HS | MCHS007 |  | 10000 | [5 empty] | 2001 | 2002 | City of McDonough | general funds
Prepare CDBG Rehabilitation Program | HS | MCHS008 |  | 25000 | [5 empty] | 2001 | 2002 | City of McDonough | general funds
Rehabilitate substandard housing throughout the City as needed | HS | MCHS009 |  | 25000 | [5 empty] | 2001 | 2005 | City of McDonough, Community Committed to Character, ALERT Team | private funds, general funds
Land Use
Develop unified development code; review and update land use regulations with county | LU | MCLU001 |  | 0 | [5 empty] | 2000 | 2002 | City of McDonough | general funds
Prepare a unified code for compatible and appropriate regulations in zoning, erosion control, development regulation, building regulation, historic preservation, tree protection, and code enforcement | LU | MCLU002 |  | 0 | [5 empty] | 2000 | 2004 | City fo McDonough | general funds
Establish policies for future annexation | LU | MCLU003 |  | 0 | [5 empty] | 2001 | 2002 | City fo McDonough | general funds
Prepare development design guidelines for City gateways | LU | MCLU004 |  | 0 | [5 empty] | 2000 | 2002 | City of McDonough Community Development | general funds
Revise zoning ordinance to allow for development in the Comprehensive Plan | LU | MCLU005 |  | 0 | [5 empty] | 2001 | 2002 | City of McDonough | general funds
Revise and update Comprehensive Plan as needed | LU | MCLU006 |  | 0 | [5 empty] | 2001 | 2004 | City of McDonough | general funds
Administrative Work Items
Update Short Term Work Program and CIE | AD | MCAD001 |  | 0 | [5 empty] | 2000 | 2004 | City of McDonough | general funds
Prepare Arts and Cultural Facilities Plan | AD | MCAD002 |  | 40000 | [5 empty] | 2000 | 2003 | City fo McDonough | general funds
Prepare facilities plan for new City Hall Structure | AD | MCAD003 |  | 25000 | [5 empty] | 2000 | 2001 | City fo McDonough | general funds
Construct new City Hall Structure | AD | MCAD004 |  | 1800000 | [5 empty] | 2001 | 2002 | City of McDonough | general funds
Expand third floor of New City Hall | AD | MCAD005 |  | 150000 | [5 empty] | 2004 | 2004 | City of McDonough | general funds
Renovate former City Hall for Public Safety and Fire Department | AD | MCAD006 |  | 250000 | [5 empty] | 2002 | 2004 | City of McDonough | general funds
Total FY 2000-2004 Expenditures |  |  |  | 40752000

## 1999 and 2000 update
FY 1999-2000 STWP update | ED=Economic Development, NH=Natural and Historic Resources, CFS=Community Facilities and Services, HS=Housing, LU=Land Use, AD=Administrative Work Item
SPLOST=Special Purpose Local-Option Sales Tax, Moreland-Altobelli=SPLOST Managers, CMAQ, Q023 = Federal Transportation Funds
General Funds=City general funds, operating revenue=city water/sewer operating funds, impact fees=water/sewer tap fees, GBT=Ben Turnipseed Engineers
HC-DOT=Henry County Department of Transportation, GaDOT=Georgia Department of Transportation, BOE=Board of Education
DCA=Department of Community Affiars, DNR=Department of Natural Resources, CDBG=Community Development Block Grant program
Project Name/Description | Plan Element | Local ID | ARC ID | Amount | FY 1999 | FY 2000 | Status | Party Responsible | Funding Source
City of McDonough
Natural and Historic Resources
Maintain cultural and historical integrity of the Downtown Square | NH | MCNH001 |  | 0 |  |  | ongoing | City of McDonough, McDonough Business Association, Advancement in McDonough (AIM), University of Georgia | Private Funds
Prepare Stormwater Master Plan and Utility Program | NH | MCNH002 |  | 50000 |  |  | 2001, pending available funding | GBT Engineers, City of McDonough | general funds, operating revenues
Create Historic District | NH | MCNH003 |  | 10000 |  |  | completed 2000 | City of McDonough, Consultant, Historic Commission | general funds, grant
Initiate a program for homeowners and businesses who are interested in having their properties listed on Federal, State, and local historic registers | NH | MCNH004 |  | 5000 |  |  | to be completed in 2002 | City of McDonough, Historic Commission | general and private funds
Maintain a registry of properties deemed historically significant for inclusion in Federal State, or local registers | NH | MCNH005 |  | 5000 |  |  | ongoing, to be completed by 2002 | City of McDonough, Consultant, Historic Commission | general funds, grant
Maintain a registry of properties deemed historically significant for inclusion in Federal State, or local registers | NH | MCNH006 |  | 5000 |  |  | ongoing, to be completed by 2002 | City of McDonough, Consultant, Historic Commission | general funds, grant
Improve substandard drainage systems throughout the City | NH | MCNH007 |  | 750000 |  |  | moved from Housing element, grant secured and first phase of construction underway in 2001 | City of McDonough, GBT Engineers, Allen-Smith Consulting | general funds, CDBG
Develop a Watershed Assessment and regulations for streams in the City | NH | MCNH008 |  | 30000 |  |  | To be completed by late 2001 for the study, regulations by 2004 | City of McDonough, GBT Engineers | general funds, operating revenues
Deleted Items from FY 2000 work program | NH |  |  | -30000 |  |  | No longer needed to hire grant administrator or to offer preservation seminars (2000) | City of McDonough, GBT Engineers | general funds, operating revenues
Economic Development
Prepare development guidelines for quality development to accommodate forecasted population increases | ED | MCED001 |  | 0 |  |  | moved to 2000 and 2001 | City of McDonough, McDonough Business Association, Advancement in McDonough (AIM), University of Georgia
Establish and maintain program to attract business and industry | ED | MCED002 |  | 0 |  |  | moved to 2002, complete in 2004 | City of McDonough
Prepare inentory of available land for suitable in-fill development | ED | MCED003 |  | 0 |  |  | complete in 2002 | City, MBA
Capital Facilities and Services
General:
Complete new Capital Improvements Plan for Transportation, Recreation, and Public Safety | CFS | MCCFS001 |  | 10000 |  |  | partially complete as part of new City Hall Structure | City of McDonough | general funds
Water and Sewer projects:
Analyze water system for leakage and pressure | CFS | MCCFS002 |  | 50000 |  |  | moved to 2000, to be complete by 2001 | City of McDonough, GBT Engineers | general funds, operating revenue
Expand water and sewer systems, line extensions, various | CFS | MCCFS004 |  | 2200000 |  |  | Kalves Creek Line completed late 1999, others extended as needed, ongoing | City of McDonough, Private Developers | operating funds, impact fees, private contributions
Enlarge Walnut Creek Wastewater Treatment Facility by 1.0 mgd | CFS | MCCFS005 |  | 0 |  |  | construction to begin in FY 2001 | GBT Engineers, City of McDonough | SPLOST, general funds, GEFA loans, impact fees
Study water infiltration of sanitary sewer systems | CFS | MCCFS006 |  | 100000 |  |  | moved to 2000, ongoing project | GBT Engineers, City of McDonough | general funds
Construct new water tank on West Side of the City at Kelly Road | CFS | MCCFS007 |  | 1000000 |  |  | completed in 2000 | GBT Engineers, City of McDonough | general funds, impact fees
Evaluate future capacity of wastewater treatment facility | CFS | MCCFS008 |  | 20000 |  |  | preliminary needs assessment completed in 2000, final policy in 2001 | GBT Engineers, City of McDonough | general funds, operating revenue
Develop projections for future demands on water and sewer capacities | CFS | MCCFS009 |  | 20000 |  |  | ongoing, short term projections finalized in late 2000 | GBT Engineers, City of McDonough | general funds, operating revenue
Evaluate proportionate share impact fees | CFS | MCCFS010 |  | 0 |  |  | moved to 2000, completion in 2001 | GBT Engineers, City of McDonough | general funds, operating revenue
Fire and EMS projects:
Maintain fire fighting ability | CFS | MCCFS011 |  | 50000 |  |  | ongoing | City of McDonough Fire Department | general funds
Transportation projects:
Thoroughfare Plan | CFS | MCCFS017 |  | 10000 |  |  | moved to 2000 beginning, complete in 2002 | City of McDonough | general funds
Parks and Recreation projects:
Study local neighborhood park needs | CFS | MCCFS027 |  | 35000 |  |  | moved to 2000, complete in 2002 | Community Development, Parks, City | general funds
Prepare maintenance plan to address existing and future recreation needs | CFS | MCCFS028 |  | 0 |  |  | moved to 2000, complete in 2002 | Community Development, Parks, City | general funds
Housing
Revise code enforcement ordinances and minimum housing standards | HS | MCHS001 |  | 5000 |  |  | completed in 2000 | City of McDonough | general funds
Establish annual review system for identifying substandard housing units | HS | MCHS002 |  | 0 |  |  | ongoing, moved to 2002 for completion | City fo McDonough
Initiate a study to determine the average single-family residence median value that represents a break-even point for services provided by the City | HS | MCHS003 |  | 10000 |  |  | moved to 2001, complete in 2002 | City fo McDonough | general funds
Revise zoning and development ordinances to provide for TND development and open spaces in new development | HS | MCHS004 |  | 5000 |  |  | moved to 2000, for completion in 2002 | City of McDonough Community Development | general funds
Prepare new development guidelines and standards that will require sidewalks, pedestrian-scale lighting, landscaping, building standards, open spaces, and conservation easements | HS | MCHS005 |  | 10000 |  |  | new subdivision and building regulations completed in 1999, more to follow in 2002 | City of McDonough | general funds
Establish committee to prepare a study on Federal Housing developments to determine their visibility and needs | HS | MCHS006 |  | 0 |  |  | moved to 2002 | City of McDonough | general funds
Initiate a market study and consumer satisfaction inquiry survey for establishing a plan to provide needed services such as affordable housing | HS | MCHS007 |  | 10000 |  |  | moved to 2002 | City of McDonough | general funds
Land Use
Develop unified development code; review and update land use regulations with county | LU | MCLU001 |  | 0 |  |  | moved to 2000, completed in 2002 | City of McDonough | general funds
Prepare a unified code for compatible and appropriate regulations in zoning, erosion control, development regulation, building regulation, historic preservation, tree protection, and code enforcement | LU | MCLU002 |  | 0 |  |  | moved to begin in 2000, with completion in 2004 | City fo McDonough | general funds
Establish policies for future annexation | LU | MCLU003 |  | 0 |  |  | moved to 2001 | City fo McDonough | general funds
Prepare development design guidelines for City gateways | LU | MCLU004 |  | 0 |  |  | beginning late 2000 for completion by 2002 | City of McDonough Community Development | general funds
Revise zoning ordinance to allow for development in the Comprehensive Plan | LU | MCLU005 |  | 0 |  |  | moved to 2002 | City of McDonough | general funds
DELETED ITEM-Hire personnel |  |  |  | -45000 |  |  | DELTED, not a capital expenditure | City of McDonough | general funds
Administrative Work Items
Update Short Term Work Program and CIE | AD | MCAD001 |  | 0 |  |  | ongoing | City of McDonough | general funds
Prepare facilities plan for new City Hall Structure | AD | MCAD003 |  | 25000 |  |  | new item added | City fo McDonough | general funds
Total FY 2000-2004 Expenditures |  |  |  | 4340000