## 2005-2009 Accomplishments
2005-2009 Report of Accomplishments | STATUS OF PROJECT OR ACTIVITY |  |  |  | **Currently underway or temporarily postponed activities or projects should appear in new STWP
Project or Activity from Previous STWP | Completed | Currently Underway | Postponed | Not Accomplished | * Explanation for Postponed or Not Accomplished Project or Activity
TRANSPORTATION
Develop Commununity Transportation Plan | X
Implement Community Transportation Plan |  | X |  |  | The estimated completion date for the implementation of the Community Transportation Plan is 2016.
Design streetscape improvements for Oakhurst Business District. | X
Design Phase 4 of Downtown Streetscapes. | X
Design uniform signage program for downtown area and neighborhood commercial districts. | X
Design Phase 5 of Downtown Streetscapes. | X
Initiate and complete signal timing study | X
Complete sidewalk improvements | X
GROWTH & LAND USE
Develop and implement design guidelines for residential infill development. | X
Complete & Implement Annexation Plan |  | X |  |  | An annexation plan has been completed and partially implemented. The City anticipates considering future annexation requests in the next 5 years.
Update of the Strategic Plan | X
Develop plan for assembly and reuse of East Trinity/East Howard corridor. | X
Citywide review of land use and zoning | X
HOUSING
Construction of Columbia Park Development |  |  |  | X | This development will not be completed due to a lack of funding.
Construction of Tally Street Lofts | X
Continue Affordable Housing Initiatives | X
COMMUNITY FACILITIES
Rennovate City Hall | X
Implement Reccomendations of Athletic Facility Master Plan. | X
Implement Storm Water Master Plan | X
Relocate Public Works facility |  | X |  |  | This task has been modified to renovate the existing Public Works facility at its current location.
Decatur MARTA Station Improvments | X
NATURAL AND CULTURAL RESOURCES
Hold Preservation Fair | X
Implementation of Preservation Corridor Plan. | X
Plant minimum of 50 trees/year on public rights of way and other public areas. | X
Provide financial support to the Woodlands | X
Complete & Implement Cemetary Master Plan | X
ECONOMIC DEVELOPMENT
Pursue redevelopment options for the Big H poperty in Oakhurst. |  | X |  |  | The current owner has found tenants for this site and continues to consider redevelopment options.
Develop advertising program focused on young entrepeneurs and business startups. | X
Locate a suitable tenant and redevelopment option for the Old Decatur Train Depot | X
Develop and implement a marketing and pubilc relations strategy for the MARTA redevelopment. | X
Develop and implement an annual retail and restaturant advertising program | X
Coordinate with DeKalb County on Callaway property development. |  | X |  |  | The Decatur Downtown Development Authority is working with DeKalb County to issue an RFP for the redevelopment of this site. The RFP responses will be reviewed in Fall 2011.

## 2010-2014 STWP
SHORT TERM WORK PROGRAM
Project or Activity | 2010 | 2011 | 2012 | 2013 | 2014 | Responsible Party | Cost Estimate | Funding Source
TRANSPORTATION
Implement Community Transportation Plan | X | X | X | X | X | City | 25000000 | City/GDOT
Implement Oakhurst Business District Streetscape Improvements |  |  | X | X |  | City/Consultant | 1000000 | City/GDOT
Implement Phase 4 of Downtown Streetscapes |  |  | X |  |  | City/Consultant | 1000000 | City/GDOT
Implement Phase 5 of Downtown Streetscapes |  |  |  | X |  | City/Consultant | 2500000 | City/GDOT
Design Clairemont/Commerce and Church/Commerce Intersection Improvements |  |  | X | X |  | City/Consultant | 250000 | City/GDOT
Design Church Street Bicycle Lanes |  |  | X | X |  | City/Consultant | 100000 | City/GDOT
Revise Parking Standards |  | X | X |  |  | City/Consultant | 20000 | City
Continue Support For Safe Routes to School | X | X | X | X | X | City | 500000 | City
GROWTH & LAND USE
Adopt A Unified Land Development Ordinance |  |  | X | X |  | City/Consultant | 100000 | City
Implement Annexation Plan |  |  | X | X | X | City | 20000 | City
Amend the Future Land Use Map to Reflect the 2010 Strategic Plan |  |  | X |  |  | City | 20000 | City
Expand the Special Pedestrian Area Zoning Overlay |  | X | X |  |  | City | 1000 | City
Encourage Redevelopment of Surface Parking Lots in Downtown Decatur | X | X | X | X | X | City/Decatur Downtown Development Authority | 50000 | City
HOUSING
Construction of Apartments at 233 East Trinity Place |  |  | X | X |  | Private Developer |  | Private
Redevelopment of Allen Wilson Terrace (Phase 2, 3 & 4) | X | X | X | X | X | Decatur Housing Authority | 13000000 | DHA/HUD
Continue Affordable Housing Initiatives | X | X | X | X | X | City/Decatur Housing Authority |  | DHA/City
COMMUNITY FACILITIES
Renovation of Fire Station 1 |  | X | X |  |  | City | 2000000 | City
Renovation of Decatur Recreation Center |  | X | X |  |  | City | 5000000 | City
Implement Storm Water Master Plan | X | X | X | X | X | City/Consultant |  | City
Renovation of Public Works Facility |  |  | X | X |  | City | 12000000 | City
NATURAL AND CULTURAL RESOURCES
Implementation of the Cemetery Master Plan | X | X | X | X |  | City | 1800000 | City
Encourage Urban Gardening | X | X | X | X | X | City |  | City/Non-profit
Adopt An Urban Forest Master Plan |  | X |  |  |  | City/Consultant | 30000 | City/Georgia Urban Forest Council
Place A Minimum of 5 Districts or Landmarks on the National Register | X | X | X | X | X | City/Consultant | 100000 | City/Non-profit
Implement the Cultural Arts Master Plan | X | X | X | X | X | City/Consultant |  | City/Non-profit
ECONOMIC DEVELOPMENT
Pursue redevelopment options for the Big H poperty in Oakhurst. | X | X | X |  |  | City/Decatur Development Authority |  | City/Decatur Development Authority
Continue to Focus Marketing and Advertising Efforts Designed to Support and Enhance the "Decatur Brand." | X | X | X | X | X | City/Decatur Development Authority |  | City/Decatur Development Authority
Explore Partnership Opportunities to Create a Business Incubator or Provide Other Incentives For Businesses in the Areas of Technology, Artisanal Manufacturing, Media Content Production Services and Similar Creative Businesses. | X | X | X | X | X | City/Decatur Development Authority |  | City/Decatur Development Authority
Improve the Landscaping and Physical Apperance of the Square. |  | X | X |  |  | City/Decatur Development Authority | 350000 | City/Decatur Development Authority
Coordinate with DeKalb County on Callaway property development. |  | X | X | X |  | City/Decatur Development Authority |  | City/Decatur Development Authority
The following supplemental plans guide the implementation of the Comprehensive Plan:
2002 Avondale Station LCI Study
2002 Athletic Facility Plan
2004 Greenway Plan
2007 Community Transportation Plan
2008 Affordable Housing Study
2009 Historic Resource Survey
2009 Parking Inventory & Policy Study
2010 Cultural Arts Master Plan
2010 Strategic Plan
2010 Decatur LCI