## STWP 2006-2016
Pine Lake’s Previous Short Term Work Plan (STWP) Accomplishments
The following table includes all the STWP items. The “X” marks the year in which those goals were expected to be either started or
completed. A “C” marks the year in which it was completed; a “P” notes that the goal was postponed; an “I” indicates that it was
initiated early; a “U” notes that the project is underway; an “R” indicates that the goal was revised; and an “N” indicates that the
initiative is no linger being considered. Currently, all activities specified for action in the 2003-2007 STWP are either still in our
working plans or are completed; therefore, none of the proposed work plans are notated with a P or an N. A single Revised element
has a footnoted explanation. All plans designated as Underway are accounted for in the 2006-2010 STWP.
X = Expected Start Date/Ongoing C = Completed P = Postponed I = Initiated/Started Early
U = Underway R = Revised N = No Longer Being Considered
2006-2010
ECONOMIC DEVELOPMENT GOAL
To achieve a growing and balanced economy, consistent with the prudent management of resources
Description | 2006 | 2007 | 2008 | 2009 | 2010 | Outcome | 2011 | 2012 | 2013 | 2014 | 2015 | 2016
Objective 1: Enlist the assistance of regional entrepreneurs in developing a destination-based economic engine.
Meet with local associations and organizations to market the business advantages of Pine Lake to Include its unique human resources | DDA Formed |  | Market plan | Rezoned |  | DDA formed; DDA members trained; Redevelopment bond obtained | Urban Redevelopment Plan | adopt final plan | Work new plan; apply for grants | U R | U R | U R
Draft grant proposals for LCI and better home towns | LCI not awarded | LCI not awarded; applied for CDBG | Received CDBG, developed Market plan | Rezoned |  | Rezoned city, received LCI-like products and resources | Follow new URP (above)
Encourage local property owners to annex into the city | added 6.6 acres | added 14.5 acres | added 8.5 acres | Law changed | added 1.5 acres | Increased business district by >400% | Follow market Plan see below
Annex the 30 acre business district adjacent to the city |  | added 14.5 acres | added 8.5 acres | Law changed | added 1.5 acres | 24.4 acres added. Market study suggested 11 more acres | work toward meeting plan goals | U | U | U R | U R | U R
Develop the business lake |  | X | U | Plans changed; eastern wetlands added | Western wetlands complete | Plans Revised: ARRA SRF for complete watershed | Lake dredging; added detention features | final plantings in spring | water quality monitoring | monitoring | monitoring | monitoring
Assess viability of annexing other properties that produce win/win |  |  | Completed as part of Market plan |  |  | Effort successfully complete 11 + 5.6 acres left to go | work on 16.6 acres or revise | U R | U R | U R | U R | U R
Rezone business district |  | I | X U C | Rezoned |  | Complete
Objective 2: Promote economic diversification of the local economic sectors.
Promote small business development | received 2 CDBG demo grants | received 4 CDBG demo grants | Market plan received 5 CDBG demo grants | sent 2 DDA members to GMA training | sent 2 DDA members to GMA training | training received; blighted areas cleared out; added alcohol lic.; down economy | U | U | U | U | U | U
Ensure that prospective business interest receive information on economic development initiatives | X | U | U | U | U | ongoing and continuing education | U | U | U | U | U | U
Develop contingency plan for possibility of no annexation and available property for business lake development |  | X | N, cancelled due to success |  |  | Plan revised; see elsewhere in STWP
COMMUNITY FACILITIES and CAPITAL IMPROVEMENTS GOAL
Objective 1: Rebuild City Hall East to provide community-based services
Provide office area for City Committees | U |  | S C |  |  | completed with State local grant
Provide office area for residents | U |  | SC |  |  | completed with state local grant
New: Rebuild the clubhouse |  |  |  | I | U | Bond ($120K) | C
Objective 2: Develop a city wide Capital Improvement Plan.
Planning for capital investments | UX | X | TAD court decision | Received Eco Bond | Used Bond to finance grant projects | $1,028,000 bond for sidewalks; wetlands; lights; cameras; clubhouse, etc | Initial funds should be spent this year | grant reimbursements should replenish for 2 yrs | U | C
Develop plans for a Municipal Complex in new district | X | X | TAD court decision | C, Received Eco Bond instead see above |  | Private plans developed to include 17-acre mixed use development were canceled due to lending changes in the economy
Engineer, design and construct sidewalks on north side of Rockbridge Rd | X | XC |  |  |  | Completed and planted ($280 K TE DOT)
Engineer context-sensitive road design for Rockbridge Rd (construction not included) |  | X | SC |  |  | Concept plan was developed with DeKalb County (now a 2014 TIP)
Develop commercial stormwater detention and overlay district | X |  |  | SC |  | Revised (see ARRA SRF)
New: Engineer, design and construct sidewalks on south side of Rockbridge Rd |  |  |  |  | X | Completed plans and transferred to DeKalb ($430K TE DOT) | unincorporated islands; better cashflow -hence DeKalb partnership
HOUSING GOAL
Objective 1: Ensure improvement of the current housing stock.
Encourage housing maintenance and rehabilitation | UX | X |  | C |  | City codes rewritten and city Rezoned
Encourage the retention of historic curbing | UX | C |  | C |  | Completed and additional curbing warehoused
Objective 2: Foster a sense of community through appropriate design standards
Promote mixed use development | UX | X | ARB developed | C |  | Completed: ARB developed, several public meetings and classes, and city rezoned
Employ design standards for new development that echoes… | UX | X |  | C |  | Completed: ARB… (see above)
Objective 3: Provide accessible and affordable housing for elderly.
Promote the development of ADA accessible housing | U |  | SC |  |  | Completed: ARB… (see above)
Seek means to provide additional financial incentives to retain older residents | UX |  |  |  |  | Developed CHDO, found Senior housing developer, applied for 9% deal; applied for HOME grant
New: Get Senior Residences | U | U | U |  | applied for 9%; received promise of HOMES | Developed CHDO, found Senior housing developer, applied for 9% deal; applied for HOME grant | Apply again; complete new URP and refile | U | U | U | U | U
NATURAL RESOURCES GOAL
Objective 1: To conserve and protect the natural and capital resources throughout Pine Lake and to advocate protection throughout Central DeKalb
Continue to coordinate with EPD… | X | X | water quality monitoring | water quality monitoring wetlands development | monitoring and integration of wetlands | An ongoing relationship is established whereby the city is expanding its environmental responsibilities | Lake dredging; added detention features | U | U | U | U | U
Objective 2: Implement and enforce environmental protection ordinance and environmental planning criteria, required by state and local ordinance for new development and advocate protection throughout Central DeKalb
Coordinate with county, state, and regional authorities to better define and categorize wetlands and recharge areas | UX | X | C |  |  | Merged with goal Objective 1 and identified in numerous SRF plans
Develop an open space recreation plan that locates and defines scenic vistas…. | U |  | SC | A Tree Authority Board was developed | City became a Tree city | Collective planning included recreational uses (DNR trails , UFC grants) | C, SRF wetlands added | Review and revise as needed
Replace and repair flume bridge… | U |  | SC |  |  | Completed, revised and competed again (319 H) | C, wetlands added, erosion control measures placed
Place erosion prevention materials along the west side of lake… | U | C | R C |  |  | Completed , revised and competed again (319h and SRF) | C, wetlands added, erosion control measures placed
…Creekbank stabilization… | U | C | R C | R C |  | Completed , revised and competed again (319h and SRF) | C, erosion control measures placed
Remove earthen dam behind Ridge apartments…. | U | SC | R C | C, erosion control measures placed |  | Completed with path added to view nature | C
Wetlands walk | X | SC | R C |  |  | Utilized 3919 H and DNR trails grant
Barry's Bog Multi-stage greenspace/watershed earthen dam behind Ridge apartments…. | X |  | SC | C, access is Henson Gateway |  | The "western wetlands" are completed with a path (319 H, Bond, and DeKalb funds)
New: Grind out gutters along curbs where DeKalb's resurfacing has buried curbs | U | SC |  |  |  | Completed and developed into comprehensive wetlands and greenspace plans
Identify and assess potential adverse impacts on conservation and recreation | [5 empty] | New to use Stormwater funds | initiated plan on first street (Spruce)
GOAL: Combined Land Use, Economic Development and Historic Resources
Objective 1: Develop a master plan for drainage program for the city’s business district
Develop a proposal for grants to plan a stormwater-retention pond in the business district | U | SC | C, a newer revised system was added |  |  | Completed, revised, and added into the wetlands/stormwater SRF
Build the stormwater-retention pond in the business district |  |  | SC | R |  | See above
Reroute the business district water… | U |  | R |  |  | See above
Objective 2: Establish a historic preservation program.
Adopt a historic preservation ordinance | U |  | R | codes developed |  | Codes developed and city rezoned
Designate historic districts | U |  | R | codes developed | City Rezoned
Create design review guidelines for historic districts | U |  |  | codes developed |  | ARB developed to review; codes established

## STWP 2011-2016
Several original items are now merged with comprehensive project plans resulting in a simplified table
2006-2010
ECONOMIC DEVELOPMENT GOAL
To achieve a growing and balanced economy, consistent with the prudent management of resources
Description | Outcome | 2011 | 2012 | 2013 | 2014 | 2015 | 2016
Objective 1: Enlist the assistance of regional entrepreneurs in developing a destination-based economic engine.
Meet with local associations and organizations to market the business advantages of Pine Lake to Include its unique human resources | DDA formed; DDA members trained; Redevelopment bond obtained | Urban Redevelopment Plan | adopt final plan | Work new plan; apply for grants | U R | U R | U R
Annex the 30 acre business district adjacent to the city | 24.4 commercial acres added. Market study suggested 11 more acres | work toward meeting plan goals | U | U | U R | U R | U R
Dredge the lake and develop comprehensive/integrated wetland | in process
Assess viability of annexing other properties that produce win/win | Effort successfully complete 11 + 5.6 acres left to go | work on 16.6 acres or revise | U R | U R | U R | U R | U R
Rezone business district | Complete
Objective 2: Promote economic diversification of the local economic sectors.
Promote small business development | training received; blighted areas cleared out; added alcohol lic.; down economy | U | U | U | U | U | U
Ensure that prospective business interests receive information on economic development initiatives | ongoing and continuing education | U | U | U | U | U | U
Utilize the arts to assist with local economy (CDBG grants, NEA, and GA Arts/Tourism Development) | received grants and implemented programs | U | U | U | U | U | U
Develop eco-tourism initiatives | research opportunities; coordinate with Capital Improvement Plan and Environment | U | U | U | U | U | U
Develop various communication resources / volunteers | Identify strategies and volunteer resources | U | U | U | U | U | U
COMMUNITY FACILITIES and CAPITAL IMPROVEMENTS GOAL
Objective 2: Develop a city wide Capital Improvement Plan.
Planning for capital investments | $1,028,000 bond for sidewalks; wetlands; lights; cameras; clubhouse, etc | Initial funds should be spent this year | grant reimbursements should replenish for 2 yrs | U | C
New: Rebuild the clubhouse | Bond ($120K) | C
NEW: Renovate BeachHosue (Bond, Tourism Grant) | CDBG |  | ?
Engineer context-sensitive road design for Rockbridge Rd (construction not included) | Concept plan was developed with DeKalb County (now a 2014 TIP) |  |  |  | advocate TIP funding
New: Engineer, design and construct sidewalks on south side of Rockbridge Rd | Completed plans and transferred project to DeKalb | DeKalb partnership | C?
Place streetscape lights in commercial district | Completed plans and transferred project to DeKalb (MARTA $70K) | DeKalb partnership | C?
HOUSING GOAL
Objective 1: Ensure improvement of the current housing stock.
Encourage housing maintenance and rehabilitation | City codes rewritten and city Rezoned | enforce code | enforce code | enforce code | enforce code | enforce code | enforce code
Promote branding of unique housing stock |  | U | U | U | U | U | U
Encourage the retention of historic curbing | Completed and additional curbing warehoused | enforce and use stock of stone curbs
Encourage retention of unique built environment |  | U | U | U | U | U | U
Objective 2: Foster a sense of community through appropriate design standards
Promote mixed use development | Completed: ARB developed, several public meetings and classes, and city rezoned | enforce | U | U | U | U | U
Objective 3: Provide accessible and affordable housing for elderly.
Promote the development of ADA accessible housing | Completed: ARB… (see above) | enforce
New: Get Senior Residences | Developed CHDO, found Senior housing developer, applied for 9% deal; applied for HOME grant | Apply again; complete new URP and refile | U | U | U | U | U
NATURAL RESOURCES GOAL
Objective 1: To conserve and protect the natural and capital resources throughout Pine Lake and to advocate protection throughout Central DeKalb
Continue to coordinate with EPD… | An ongoing relationship is established whereby the city is expanding its environmental responsibilities | Lake dredging; added detention features | U | U | U | U | U
Objective 2: Implement and enforce environmental protection ordinance and environmental planning criteria, required by state and local ordinance for new development and advocate protection throughout Central DeKalb
Coordinate with county, state, and regional authorities to better define and categorize wetlands and recharge areas | Merged with goal Obj 1 and identified in numerous SRF plans | meet comprehensive environmental. goals | U | U | U | U | U
Develop an open space recreation plan that locates and defines scenic vistas…. | Collective planning included recreational uses (DNR trails , UFC grants) | C, SRF wetlands added | Review and revise as needed | U | U | U | U
Place erosion prevention materials along the west side of lake… | Completed , revised and competed again (319h and SRF) | C, wetlands added, erosion control measures placed | maintain | U | U | U | U
Implement Creekbank stabilization | Completed, revised and competed again (319h and SRF) | C, erosion control measures placed | maintain | U | U | U | U
Maintain all wetlands |  |  | maintain | U | U | U | U