The East Point City Council adopted the East Point 2007-2011 Short Term Work Program (STWP) as a part of the 2026 Comprehensive Plan Update October 16, 2006.  As required under the Minimum Planning Standards and Procedures for Local Comprehensive Planning, a summary of accomplishments is provided below.  The status of each action item will be identified as Completed, Deleted or Reprogrammed.

Economic Development

- Enhance the attractiveness of the community

Estimated Cost: Unknown

Funding Source: City of East Point

Scheduled Year: 2007-2011

Responsibility: City of East Point

Reprogrammed as on-going for FY 2012-FY2016

- Convene Board of Education and Community Work Sessions

Estimated Cost: No Cost

Funding Source: City of East Point

Scheduled Year: 2007-2011

Responsibility: City of East Point

Deleted – Not the responsibility of the City

- Convene community meetings aimed at organizing a community group network utilizing the East Point Newsletter

Estimated Cost: $500

Funding Source: City of East Point

Scheduled Year: 2007-2011

Responsibility: City of East Point

Deleted – Focus shifted.  Community meetings were held and a group formed, but not related to newsletter

- Focus East Point Business and Industrial Development Authority and Economic Development staff resources in the Downtown

Estimated Cost: No Cost

Funding Source: City of East Point

Scheduled Year: 2007-2011

Responsibility: City of East Point/ East Point Business and Industrial Development Authority

Reprogrammed as on-going for FY 2012-FY 2016

- Devise and implement a capital improvement project in the Downtown

Estimated Cost: Unknown

Funding Source: City of East Point/ Municipal Electric Authority of Georgia

Scheduled Year: 2007-2011

Responsibility: City of East Point/ East Point Business and Industrial Development Authority

Reprogrammed – based on 2010-2011 Council Project List.  Hotel/Motel Tax to be included as additional funding source – FY 2012-FY 2017

- Focus East Point Business and Industrial Development Authority and Economic Development staff resources in the Old Fourth Ward

Estimated Cost: No Cost

Funding Source: City of East Point

Scheduled Year: 2007-2011

Responsibility: City of East Point/ East Point Business and Industrial Development Authority

Reprogrammed FY 2012- FY 2017.

- Devise and implement a capital improvement project in the Old Fourth Ward

Estimated Cost: Unknown

Funding Source: City of East Point – Municipal Electric Authority of Georgia

Scheduled Year: 2007-2011

Responsibility: City of East Point/ East Point Business and Industrial Development Authority

Reprogrammed FY 2012 – FY 2017

- Focus East Point Business and Industrial Development Authority and Economic Development staff resources on Cleveland Avenue Estimated Cost: No Cost

Funding Source: City of East Point

Scheduled Year: 2007-2011

Responsibility: City of East Point/ East Point Business and Industrial Development Authority

Reprogrammed as on-going for FY 2012-FY 2016

- Revise and implement a capital improvement project on Cleveland Avenue

Estimated Cost: Unknown

Funding Source: City of East Point – Municipal Electric Authority of Georgia

Scheduled Year: 2007-2011

Responsibility: City of East Point/ East Point Business and Industrial Development Authority

Reprogrammed- This area is a redevelopment focus area within the East Point Corridors TAD

- Designate target areas and establish loan pool

Estimated Cost: $50,000

Funding Source: City of East Point/ CDBG monies

Scheduled Year: 2008

Responsibility: City of East Point

Reprogrammed as on-going for FY 2013 –focus on residential rehab for low income and senior citizens

- Characterize vacant industrial buildings and structures

Estimated Cost: $500

Funding Source: City of East Point

Scheduled Year: 2007

Responsibility: City of East Point

Reprogrammed as on-going changing the term “characterize” to “identify market”

- Devise “triage” strategy and contact property owners Estimated Cost: $1000

Funding Source: City of East Point

Scheduled Year: 2008

Responsibility: City of East Point

Deleted – Not sure of original intent

- Initiate abandoned structure removal and site clearance

Estimated Cost: $ 40,000

Funding Source: City of East Point/ Municipal Electric Authority of Georgia

Scheduled Year: 2008-2010

Responsibility: City of East Point

Reprogrammed as part of 50 Worst Properties Program

- Coordinate contact with Brownfield site owners and EPD

Estimated Cost: No cost

Funding Source: City of East Point

Scheduled Year: 2007–2011

Responsibility: City of East Point

Reprogrammed as on-going for FY 2012-FY 2016 – Focus area is Lawrence Street

- Explore business participation in jobs training

Estimated Cost: No cost

Funding Source: City of East Point

Scheduled Year: 2008

Responsibility: City of East Point

Reprogrammed as on-going FY 2012-FY 2016

16.	Investigate the establishment of a pilot jobs training program

Estimated Cost: $10,000

Funding Source: City of East Point

Scheduled Year: 2007

Responsibility: City of East Point

Deleted-City partners with County and State on job training

- Formalize job training program as appropriate

Estimated Cost: $20,000 per year

Funding Source: City of East Point/ CDBG monies/ Municipal Electric Authority of Georgia

Scheduled Year: 2008–2011

Responsibility: City of East Point

Reprogrammed to focus on Summer Youth Jobs Program FY 2012 – FY 2017

- Explore support for jobs access program

Estimated Cost: Unknown

Funding Source: City of East Point

Scheduled Year: 2007

Responsibility: City of East Point

Deleted-City partners with County and State on job training

- Investigate the establishment of a pilot program for jobs access

Estimated Cost: $2,500

Funding Source: City of East Point

Scheduled Year: 2007

Responsibility: City of East Point

Deleted-City partners with County and State on job training

20. 	Formalize jobs access program as appropriate

Estimated Cost: $5,000 per year

Funding Source: City of East Point/ CDBG monies

Scheduled Year: 2007 – 2011

Responsibility: City of East Point

Deleted-City partners with County and State on job training

- Create an Economic Development Campaign

Estimated Cost: $10,000

Funding Source: Business and Industrial Development Authority

Scheduled Year: 2009

Responsibility: Business and Industrial Development Authority

Reprogrammed as on-going for FY 2012-FY 2013.  Plan to start October 2011

- Craft Development Package and Incentives

Estimated Cost: $12,500

Funding Source: Business and Industrial Development Authority

Scheduled Year: 2009-2010

Responsibility: Business and Industrial Development Authority

Reprogrammed as on-going for FY 2012-FY 2016.  Incentives vary by prospect

- Utilize Community Improvement District (CID) efforts for self promotion, and fundraising for future events/ improvement projects

Estimated Cost: Unknown

Funding Source: Unknown

Scheduled Year: 2008 - 2011

Responsibility: City of East Point/ City of Atlanta/ CID

Deleted – CID implementation plan completed but businesses owners did not agree to participate when time to accept financial responsibility

- Develop a public/ private partnership for development of the city owned property at the north Central Business District Area

Estimated Cost: Unknown

Funding Source: City of East Point

Scheduled Year: 2008-2010

Responsibility: City of East Point

Deleted- Not specific to an area of the City.  Working on partnership for downtown properties

- Create a partnership with Business and Industrial Development Authority to help develop the City owned properties

Estimated Cost: Unknown

Funding Source: City of East Point

Scheduled Year: 2008-2010

Responsibility: City of East Point

Reprogrammed as on-going partnership between City and BIDA for redevelopment of Commons Property

- Implement the Tax Allocation District for redevelopment within the Downtown

Estimated Cost: Unknown

Funding Source: City of East Point

Scheduled Year: 2008

Responsibility: City of East Point

Completed.  Includes Main Street, and nodes along Cleveland Avenue and Washington Road. Approved by City and Fulton County.  Awaiting approval for Fulton BOE.

- Market an Incentive Package for infill residential projects

Estimated Cost: $10,000 per year

Funding Source: City of East Point/ Municipal Electric Authority of Georgia

Scheduled Year: 2007–2011

Responsibility: City of East Point/ East Point Business and Industrial Development Authority

Deleted- Not economically feasible in this market

- Locate the Main Street Manager office in downtown

Estimated Cost: $20,000

Funding Source: City of East Point

Scheduled Year: 2009

Responsibility: City of East Point

Reprogrammed and will occur if municipal complex is constructed FY 2012- FY 2014.  Title change to Downtown Business Development Coordinator

29. Enhance the East Point web page to include a tourism and business recruitment page focusing on downtown

Estimated Cost: $5,000

Funding Source: City of East Point

Scheduled Year: 2007

Responsibility: City of East Point

Completed

Natural and Historic Resources

- Update the East Point Tree Ordinance

Estimated Cost: $1,500

Funding Source: City of East Point

Scheduled Year: 2008

Responsibility: City of East Point

Completed under March 2009 Zoning Ordinance & Development Code

- Update the East Point Buffer Ordinance

Estimated Cost: $1,500

Funding Source: City of East Point

Scheduled Year: 2008

Responsibility: City of East Point

Completed under March 2009 Zoning Ordinance & Development Code

- Update the East Point Wetland/ Floodplain Ordinance

Estimated Cost: $1,500

Funding Source: City of East Point

Scheduled Year: 2008

Responsibility: City of East Point

Completed under March 2009 Zoning Ordinance & Development Code

- Update the East Point Soil Erosion Control Measures Ordinance

Estimated Cost: $ 1,500

Funding Source: City of East Point

Scheduled Year: 2008

Responsibility: City of East Point

Completed under March 2009 Zoning Ordinance & Development Code

- Encourage the preservation of existing single-family homes with historic character

Estimated Cost: Unknown

Funding Source: City of East Point

Scheduled Year: 2007-2011

Responsibility: City of East Point

Completed under March 2009 Zoning Ordinance & Development Code (Infill Ordinance)

- Promote new residential development that is keeping with the historic style and character of the surrounding neighborhoods, including higher density developments

Estimated Cost: Unknown

Funding Source: City of East Point

Scheduled Year: 2008-2011

Responsibility: City of East Point

Completed under March 2009 Zoning Ordinance & Development Code (Infill Ordinance)

- Encourage local property owners to apply for historic housing tax credits

Estimated Cost: Unknown

Funding Source: City of East Point

Scheduled Year: 2006-2010

Responsibility: City of East Point

Deleted – Not sure how this was to be implemented

Greenspace and Recreation

- Conduct a feasibility analysis for parks and community open spaces

Estimated Cost: $20,000

Funding Source: City of East Point

Scheduled Year: 2009

Responsibility: City of East Point

Completed 2010 Parks & Recreation Master Plan

- Draft and adopt a Greenspace/ Open Space Ordinance

Estimated Cost: $1,500

Funding Source: City of East Point

Scheduled Year: 2007

Responsibility: City of East Point

Incorporated in Subdivision Regulations – March 2009 Zoning Ordinance & Development Code

- Review the availability of the Governor’s greenspace program for the acquisition of the passive park areas for the community

Estimated Cost: Unknown

Funding Source: City of East Point

Scheduled Year: 2008-2009

Responsibility: City of East Point

Completed

- Investigate the feasibility of a linear park trail system Estimated Cost: $10,000

Funding Source: City of East Point/ Department of Community Affairs

Scheduled Year: 2009

Responsibility: City of East Point

Completed in 2010 Parks & Recreation Master Plan

- Accept dedication and acquire parkland sites

Estimated Cost: $50,000

Funding Source: City of East Point

Scheduled Year: 2007-2011

Responsibility: City of East Point

Completed -Addressed in 2010 Parks & Recreation Master Plan

- Design and build park and trail system segments

Estimated Cost: $100,000

Funding Source: City of East Point/ Private Investments Scheduled Year: 2010

Responsibility: City of East Point

Completed -Addressed in 2010 Parks & Recreation Master Plan

Housing

- Stabilize and increase the housing stock

Estimated Cost: Unknown

Funding Source: City of East Point

Scheduled Year: 2007-2011

Responsibility: City of East Point

Deleted – Not sure how this was to be implemented

- Implement an Affordable Housing Incentive Ordinance

Estimated Cost: $1,500

Funding Source: City of East Point

Scheduled Year: 2007

Responsibility: City of East Point

Reprogrammed as on-going FY 2012 – FY 2017

- Implement Affordable Housing Tax Credit

Estimated Cost: Unknown

Funding Source: Private Businesses

Scheduled Year: 2008

Responsibility: City of East Point

Deleted – Applications usually submitted by Developer not City

- Housing 203(K) Rehabilitation Program (CDBG)

Estimated Cost: Unknown

Funding Source: HUD

Scheduled Year: 2008 - 2011

Responsibility: City of East Point

Deleted – CDBG funds allocated via Fulton County

- Down-payment Assistance Program

Estimated Cost: Unknown

Funding Source: Private Businesses

Scheduled Year: 2009

Responsibility: Local Employers

Deleted – Program implemented via Fulton County

- Consider using land write-down to develop more loft housing

Estimated Cost: $2,500

Funding Source: Business and Industrial Development Authority

Scheduled Year: 2007

Responsibility: Business and Industrial Development Authority

Deleted – Not economically feasible due to housing downturn

- Create a housing conditions data system

Estimated Cost: $500

Funding Source: City of East Point

Scheduled Year: 2008

Responsibility: City of East Point

Reprogrammed as part of 50 Worst Properties Program

- Investigate housing rehabilitation grant and loan programs to facilitate housing rehabilitation

Estimated Cost: $20,000 per year

Funding Source: City of East Point/ Fulton County

Scheduled Year: 2007-2008

Responsibility: City of East Point

Reprogrammed to investigate and implement a program in the City

- Draft and Adopt an Affordable Housing Ordinance

Estimated Cost: $2,000

Funding Source: City of East Point

Scheduled Year: 2007

Responsibility: City of East Point

Deleted – City has existing affordable housing that is vacant

- Facilitate a loan fund to buy-down mortgage rates

Estimated Cost: $50,000 per year

Funding Source: City of East Point/ CDBG monies

Scheduled Year: 2007-2011

Responsibility: City of East Point

Deleted – CDBG funds allocated via Fulton County

- Investigate central business district and Transit Orientated Development areas for more housing options with higher densities

Estimated Cost: $25,000

Funding Source: City of East Point/ Fulton County

Scheduled Year: 2008

Responsibility: City of East Point

Reprogrammed under LCI Supplemental Study FY 2012

54. Revise Overlay Districts to include Transit Orientated Development

Estimated Cost: $50,000

Funding Source: City of East Point

Scheduled Year: 2008

Responsibility: City of East Point

Reprogrammed under LCI Supplemental Study FY 2012

Land Use

- Adopt additional guidelines for the Central Business District

Estimated Cost: $5,000

Funding Source: City of East Point

Scheduled Year: 2008

Responsibility: City of East Point

Completed under March 2009 Zoning Ordinance & Development Code.  Additional programming under LCI Supplemental Study FY 2012

- Amend Zoning Ordinance to allow redevelopment of Lawrence Street Brownfield site

Estimated Cost: $6,500

Funding Source: City of East Point

Scheduled Year: 2008

Responsibility: City of East Point

Reprogrammed under Mission 2036 Comprehensive Plan Update FY 2012

- Prepare additional architectural/ design guidelines for new developments in overlay district Estimated Cost: $10,000

Funding Source: City of East Point

Scheduled Year: 2009

Responsibility: City of East Point

Deleted – Area not defined

- Develop regulations to guide historic preservation

Estimated Cost: $15,000

Funding Source: City of East Point

Scheduled Year: 2009

Responsibility: City of East Point

Reprogrammed -May be addressed under Mission 2036 Comprehensive Plan Update FY 2012

- Develop Community Overlay Districts and architectural guidelines to guide infill development

Estimated Cost: $5,000

Funding Source: City of East Point

Scheduled Year: 2009

Responsibility: City of East Point

Deleted – Area not defined

March 2009 Zoning Ordinance & Development Code includes Infill Ordinance

- Amend/ update the Zoning Ordinance to reflect recommendations made as part of the LCI Study

Estimated Cost: $2,500

Funding Source: City of East Point

Scheduled Year: 2007

Responsibility: City of East Point

Completed under March 2009 Zoning Ordinance & Development Code

- Apply for Environmental Protection Agency’s Brownfield Grant for site assessment

Estimated Cost: $10,000

Funding Source: Unknown

Scheduled Year: 2007-2011

Responsibility: City of East Point

Reprogrammed to focus on Lawrence Street area FY 2012 – FY 2017

- Apply for Environmental Protection Agency’s Brownfield Grant for clean-up

Estimated Cost: $10,000

Funding Source: Unknown

Scheduled Year: 2007-2011

Responsibility: City of East Point

Reprogrammed to focus on Lawrence Street area FY 2012 – FY 2017

- Apply for Environmental Protection Agency’s Brownfield Grant for revolving loan monies

Estimated Cost: $10,000

Funding Source: Unknown

Scheduled Year: 2007-2011

Responsibility: City of East Point

Reprogrammed to focus on Lawrence Street area FY 2012 – FY 2017

- Application for LCI implementations funds

Estimated Cost: $10,000

Funding Source: Unknown

Scheduled Year: 2008

Responsibility: City of East Point

Reprogrammed as LCI Supplemental Study FY 2012 for Downtown.  Application being drafted for pedestrian, bike and streetscape improvements along East Point Street

- Conduct a feasibility analysis for an entertainment district at the brownfield redevelopment site

Estimated Cost: $20,000

Funding Source: City of East Point

Scheduled Year: 2009

Responsibility: City of East Point

Reprogrammed - May be addressed under Mission 2036 Comprehensive Plan Update FY 2012

- Develop new civic green and public buildings for the central business district

Estimated Cost: $2,500,000

Funding Source: City of East Point

Scheduled Year: 2009

Responsibility: City of East Point

Reprogrammed as larger Municipal Complex development FY 2012-FY 2014

- Amend the City Zoning Ordinance and Future Land Use Map as indicated in the adopted Comprehensive Plan

Estimated Cost: $2,500

Funding Source: City of East Point

Scheduled Year: 2009

Responsibility: City of East Point

Completed

- Amend the Zoning Ordinance to support Smart Growth policies to implement the Comprehensive Plan

Estimated Cost: $2,500

Funding Source: City of East Point

Scheduled Year: 2009

Responsibility: City of East Point

Completed

Police Department

- Vehicles/ Replace

Estimated Cost: $500,000

Funding Source: City of East Point

Scheduled Year: 2007-2011

Responsibility: City of East Point

Completed

- Equipment/ New

Estimated Cost: $140,000

Funding Source: City of East Point

Scheduled Year: 2007-2011

Responsibility: City of East Point

Completed

- Equipment/ Replace

Estimated Cost: $12,000

Funding Source: City of East Point

Scheduled Year: 2007–2011

Responsibility: City of East Point

Completed

Fire Department

- Reduce the number of fires and fire deaths through target public education programs.

Estimated cost: $300,000

Funding Source: Federal Grant

Scheduled Year: 2007

Responsibility: East Point Fire Department

Reprogrammed Annually

- Administration office facility

Estimated cost: $1,110,000

Funding Source: Unidentified

Scheduled Year: 2008

Responsibility: City of East Point

Reprogrammed – Will occur under Municipal Complex development

- Complete requirements to become accredited agency/department

Estimated Cost: $ 5,000

Funding Source: General Funds

Scheduled Year: 2008

Responsibility: East Point Fire Department

Reprogrammed FY 2012-FY 2017

- Develop an education incentive for firefighters with college credits

Estimated cost: $560,000

Funding Source: General Fund

Scheduled Year: 2009

Responsibility: City of East Point

Reprogrammed FY 2012-FY 2017

- Create a Fire Cadet Program to prepare students for future careers in fire service

Estimated cost: $122,500

Funding Source: Capital Budget

Scheduled Year: 2009

Responsibility: East Point Fire Department

Reprogrammed FY 2012-FY 2017

- Develop a partnership with marketing agencies and local media to improve relationships and public image

Estimated cost: $100,000

Funding Source: Grant/ In-kind

Scheduled Year: 2008

Responsibility: East Point Fire Department

Reprogrammed FY 2012-FY 2017

- Replace Fire Station # 1 (55 years old)

Estimated cost: $1,800,000

Funding Source: General Fund

Scheduled Year: 2009

Responsibility: City of East Point

Deleted – New site for proposed Municipal Complex

- Replace Fire Station # 4 (46 years old)

Estimated cost: $1,200,000

Funding Source: General Fund

Scheduled Year: 2009

Responsibility: City of East Point

Reprogrammed FY 2012- FY 2017

- Replace Fire Station # 5 (35 years old)

Estimated cost: $1,200,000

Funding Source: General Fund

Scheduled Year: 2010

Responsibility: City of East Point

Reprogrammed – Station donated to Parks & Recreation FY 2008

- Bullard thermal imaging camera

Estimated cost: $72,000

Funding Source: General Fund

Scheduled Year: 2007-2011

Responsibility: East Point Fire Department

Completed – Funds allocated under FY 2011 Budget

- Create a public safety Training Facility to provide learning and training environment for police and fire

Estimated cost: $1,997,500

Funding Source: Unidentified

Scheduled Year: 2010

Responsibility: City of East Point

Reprogrammed FY 2012-FY 2017

- Create a large storage facility to store equipment and confidential files, documents, and evidence

Estimated cost: $605,000 each year

Funding Source: unidentified

Scheduled Year: 2009

Responsibility: East Point Fire Department

Completed under FY 2008 Budget

- Implement ten year apparatus lease purchase replacement plan

Estimated cost: $160,000 each year

Funding Source: General Fund

Scheduled Year: 2010

Responsibility: East Point Fire Department

Completed Phase I FY 2011.  Reprogrammed FY 2012-FY 2017

- Replace Fire Engine # 2

Estimated cost: $450,000

Funding Source: Capital Budget

Scheduled Year: 2007

Responsibility: East Point Fire Department

Completed Phase I FY 2011.  Reprogrammed in FY 2012-FY 2017

- Replace Fire Engine # 5

Estimated cost: $450,000

Funding Source: Capital Budget

Scheduled Year: 2007

Responsibility: East Point Fire Department

Completed Phase I FY 2011

- Replace ladder truck # 4

Estimated cost: $1,000,000

Funding Source: Capital Budget

Scheduled Year: 2009

Responsibility: East Point Fire Department

Deleted

- Purchase Breathing Apparatuses and face pieces

Estimated cost: $300,000

Funding Source: Capital Budget

Scheduled Year: 2007

Responsibility: East Point Fire Department

Completed – Funds allocated FY 2007

- Replace Hurst Tools

Estimated cost: $69,138

Funding Source: Capital Budget

Scheduled Year: 2008

Responsibility: East Point Fire Department

Completed

- Replace Cardiac Monitors

Estimated cost: $60,000

Funding Source: Capital Budget

Scheduled Year: 2007

Responsibility: East Point Fire Department

Reprogrammed in FY 2012-FY 2017

- Provide two sets of personal protective clothing for all employees (turnout gear, boots, helmets, gloves, etc.

Estimated cost: $550,000

Funding Source: Capital Budget

Scheduled Year: 2007-2011

Responsibility: East Point Fire Department

Reprogrammed in FY 2012

- Install mobile data terminals in all fire trucks and emergency vehicles

Estimated cost: $261,000

Funding Source: Federal grant

Scheduled Year: 2007

Responsibility: East Point Fire Department

Completed FY 2009

- Purchase guns, holsters, vest, and cuffs for Fire

Estimated cost: $5,000

Funding Source: General Fund

Scheduled Year: 2008

Responsibility: East Point Fire Department

Completed FY 2009

- Purchase N. F. P.A. code books

Estimated cost: $6,000

Funding Source: General Fund

Scheduled Year: 2009

Responsibility: East Point Fire Department

Completed

- Vehicles/ 3-year replacement cycle

Estimated cost: $50,000 per year

Funding Source: Capital Budget

Scheduled Year: 2007-2011

Responsibility: East Point Fire Department

Reprogrammed in FY 2012-FY 2017

- Create Training Coordinator (Captain) position

Estimated cost: $75,000 per year

Funding Source: General Fund

Scheduled Year: 2008

Responsibility: East Point Fire Department

Reprogrammed FY 2012-FY 2017

- Create Emergency Medical Coordinator (Captain) position

Estimated cost: $75,000

Funding Source: General Fund

Scheduled Year: 2008

Responsibility: East Point Fire Department

Deleted-No funding for additional positions

- Create Paramedic Instructor position

Estimated cost: $55,000

Funding Source: General Fund

Scheduled Year: 2010

Responsibility: East Point Fire Department

Deleted – No funding for additional positions

- Provide CPR classes to community

Estimated cost: $1,500 per year

Funding Source: General Fund

Scheduled Year: 2008-2011

Responsibility: East Point Fire Department

Reprogrammed Annually

- Purchase equipment for paramedic program

Estimated cost: $200,000

Funding Source: Capital Budget

Scheduled Year: 2010

Responsibility: East Point Fire Department

Reprogrammed FY 2012-FY 2017

- Provide Community Deputy Fire Marshal training

Estimated cost: $1,000 per year

Funding Source: General Fund

Scheduled Year: 2007-2011

Responsibility: East Point Fire Department

Reprogrammed Annually

- Personnel to satisfy SAFER grant

Estimated cost: $ 3,750,000

Funding Source: Federal Grant/ General Fund

Scheduled Year: 2007 - 2011

Responsibility: East Point Fire Department

Completed in FY 2007-FY 2008 Budgets

- Additional support personnel positions in order to meet the objectives of the Fire Department and the Community

Estimated cost: $100,000

Funding Source: General Fund

Scheduled Year: 2008

Responsibility: East Point Fire Department

Deleted-No funding for additional positions

- Additional operations personnel to reduce overtime budget

Estimated cost: $940,000

Funding Source: General Fund

Scheduled Year: 2008

Responsibility: East Point Fire Department

Completed in FY 2012 Budget

- Replace fire hose

Estimated cost: $278,000

Funding Source: General Fund

Scheduled Year: 2008-2009

Responsibility: East Point Fire Department

Reprogrammed FY 2012-FY 2017

- Scotty Fire Safety House

Estimated cost: $40,175

Funding Source: General Fund

Scheduled Year: 2009

Responsibility: East Point Fire Department

Reprogrammed FY 2012-FY 2017

Department of Public Works

- Institute “volume-based” refuse collection program

Estimated Cost: No Cost

Funding Source: City of East Point

Scheduled Year: 2008

Responsibility: City of East Point

May be addressed under Solid Waste Management Plan FY 2011-FY 2012

- Sanitation Department vehicle and equipment purchases

Estimated Cost: $750,000

Funding Source: City of East Point

Scheduled Year: 2009

Responsibility: City of East Point

Completed

- Fund City rights-of-way and capital improvements costs

Estimated Cost: $1,000,000

Funding Source: City of East Point/ Georgia Department of Transportation

Scheduled Year: 2007–2011

Responsibility: City of East Point

Completed

- Control groundwater infiltration as needed

Estimated Cost: Unknown

Funding Source: City of East Point

Scheduled Year: 2007–2011

Responsibility: City of East Point

Deleted – Not sure of issue that was to be addressed

Recommended Gateway Projects

- Old Cleveland Avenue

Estimated Cost: $354,500

Funding Source: City of East Point

Scheduled Year: 2008

Responsibility: City of East Point/ Local

Reprogrammed for FY 2012-FY 2016

- South Fulton Medical Center Gateway Park and Pavilion

Estimated Cost: $578,500

Funding Source: SFMC

Scheduled Year: 2008

Responsibility: City of East Point/ South Fulton Medical Center

Completed

- City Limits Gateway and Roundabout

Estimated Cost: $453,500

Funding Source: City of East Point/ City of Atlanta/ Community Improvement District Grant/ Local Development Fund/ Livable Centers Initiative Grant

Scheduled Year: 2009

Responsibility: City of East Point/ City of Atlanta

Reprogrammed FY 2012-FY 2016

- I-85 Gateway

Estimated Cost: $35,000

Funding Source: City of East Point/ Community Improvement District Grant

Scheduled Year: 2009

Responsibility: City of East Point/ City of Atlanta

Completed

Recommended Connectivity Projects

Projects in this section Reprogrammed as Long Range (beyond FY 2017)

- Explore feasibility of opening east/west and north/south connectors throughout the City

Estimated Cost: $2,500

Funding Source: City of East Point

Scheduled Year: 2008

Responsibility: City of East Point

- Clermont Extension

Estimated Cost: $1,100,000

Funding Source: City of East Point/ Tax Allocation District

Scheduled Year: 2009

Responsibility: City of East Point

- St. Francis Extension

Estimated Cost: $2,970,000

Funding Source: City of East Point/ Tax Allocation District

Scheduled Year: 2010

Responsibility: City of East Point

- St. Joseph Extension

Estimated Cost: $2,310,000

Funding Source: City of East Point/ Tax Allocation District

Scheduled Year: 2011

Responsibility: City of East Point

Recommended Streetscape Improvements

Projects in this section Reprogrammed as Long Range (beyond FY 2017) except as noted

- Main Street to Norman Berry

Estimated Cost: $2,070,500

Funding Source: City of East Point/ Transportation Enhancement Program/ Livable Centers Initiative Grant

Scheduled Year: 2008

Responsibility: City of East Point

- Norman Berry to Sylvan

Estimated Cost: $1,122,200

Funding Source: City of East Point/ Transportation Enhancement Program/ Livable Centers Initiative Grant

Scheduled Year: 2008

Responsibility: City of East Point

- Sylvan to Metropolitan

Estimated Cost: $1,124,500

Funding Source: City of East Point/ Transportation Enhancement Program/ Livable Centers Initiative Grant

Scheduled Year: 2009

Responsibility: City of East Point/ City of Atlanta

- Main Street

Estimated Cost: $2,314,400

Funding Source: Transportation Enhancement Program

Scheduled Year: 2009

Responsibility: City of East Point

TE Grant currently in progress.  NTP for R-O-W acquisition received 08/24/201.  FY 2011-FY 2014

- East Point Street

Estimated Cost: $2,777,280

Funding Source: Transportation Improvement Program

Scheduled Year: 2009

Responsibility: City of East Point

Reprogrammed for FY 2014

- Semmes Street

Estimated Cost: $1,265,000

Funding Source: Transportation Improvement Program

Scheduled Year: 2010

Responsibility: City of East Point

Reprogrammed FY 2013

- Ware Avenue

Estimated Cost: $1,342,000

Funding Source: Transportation Improvement Program

Scheduled Year: 2010

Responsibility: City of East Point

- West Taylor Avenue

Estimated Cost: $495,000

Funding Source: Transportation Improvement Program

Scheduled Year: 2011

Responsibility: City of East Point

Recommended Pedestrian and Bicycle Improvements

Projects in this section Reprogrammed as Long Range (beyond FY 2017) except as noted

- Trail System along Cleveland Avenue

Estimated Cost: $1,124,500

Funding Source: Georgia Department of Transportation/ Livable Centers Initiative Grant

Scheduled Year: 2009

Responsibility: City of East Point/ City of Atlanta

- Cleveland Avenue

Estimated Cost: $473,000

Funding Source: Transportation Improvement Program

Scheduled Year: 2009

Responsibility: City of East Point

- Dunlap Street

Estimated Cost: $275,000

Funding Source: City of East Point

Scheduled Year: 2010

Responsibility: City of East Point

Recommended Roadway Widening and Intersection Improvements

Projects in this section Reprogrammed as Long Range (beyond FY 2017) except as noted

- Widen Washington Road from 1-285 to Desert Drive, including intersection improvements at Hammarskjold Avenue, Janice Drive, and Camel Drive (segment 1 of 3)

Estimated Cost: $5,202,240

Funding Source: City of East Point/ Transportation Improvement Program

Scheduled Year: 2006-2010

Responsibility: City of East Point

Reprogrammed FY 2017

- Washington Road from State Route 6 (Camp Creek Parkway) to DeLowe Drive (segment 2 of 3)

Estimated Cost: $1,631,000

Funding Source: City of East Point/ Transportation Improvement Program

Scheduled Year: 2006-2010

Responsibility: City of East Point/ City of Atlanta

Reprogrammed FY 2017

- Washington Road from DeLowe Drive to Legion Way (segment 3 of 3)

Estimated Cost: $644,000

Funding Source: City of East Point/ Transportation Improvement Program

Scheduled Year: 2006-2010

Responsibility: City of East Point/ City of Atlanta

Reprogrammed FY 2017

- Widen Headland Drive from western City limit to Ben Hill Road

Estimated Cost: $270,000

Funding Source: City of East Point/ Transportation Improvement Program

Scheduled Year: 2010

Responsibility: City of East Point

- Widen Sylvan Road from Oakleigh Drive to northern City limit

Estimated Cost: $530,000

Funding Source: City of East Point/ Transportation Improvement Program

Scheduled Year: 2011

Responsibility: City of East Point

- Widen Virginia Avenue from western City limit to eastern City limit

Estimated Cost: Unknown

Funding Source: City of East Point/ Transportation Improvement Program

Scheduled Year: 2011

Responsibility: City of East Point

Other Improvements

- Synchronize Traffic Lights along Cleveland Avenue

Estimated Cost: Unknown

Funding Source: City of East Point/ City of Atlanta

Scheduled Year: 2009

Responsibility: City of East Point/ City of Atlanta

Reprogrammed FY 2013

- Enter into negotiations with MARTA on South parking lot

Estimated Cost: No cost

Funding Source: Business and Industrial Development Authority

Scheduled Year: 2008

Responsibility: Business and Industrial Development Authority

Reprogrammed under LCI Supplemental Study FY 2012

- Work with the Georgia Department of Transportation to ensure that plans of development compliment each other

Estimated Cost: No cost

Funding Source: City of East Point

Scheduled Year: 2007-2011

Responsibility: City of East Point

Reprogrammed FY 2012

- Submit recommendations to Atlanta Regional Commission for placement of Transportation Improvement Program

Estimated Cost: No cost

Funding Source: City of East Point

Scheduled Year: 2008

Responsibility: City of East Point

Reprogrammed FY 2012

- Apply for another Transportation Enhancement Funds (TEA) for Main Street

Estimated Cost: No cost

Funding Source: City of East Point

Scheduled Year: 2008

Responsibility: City of East Point

Completed and Reprogrammed FY 2012- FY 2017

141.	Fund strategic transportation linkages Estimated Cost: $50,000

Funding Source: City of East Point

Scheduled Year: 2009–2010

Responsibility: City of East Point

Reprogrammed as Long Range (beyond FY 2017)

- U.S.19/41 (Tara Boulevard) Arterial Bus Rapid Transfer

Estimated Cost: $27,600,000

Funding Source: Transportation Improvement Program

Scheduled Year: 2010

Responsibility: Multiple Counties and Municipalities

Reprogrammed as Long Range (beyond FY 2017)