## STWP Form-Economic Development
East Point Short Term Work Program
Short Term Work Program Update 2011 - 2016
Comprehensive Plan Element: | Economic Development
Section:
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Complete Citywide Economic Development Strategic Plan | FY 2011 | FY 2012 | 80000 | Economic Development | General Fund | RFP consultant selection in progress.
Complete Downtown-Ft. McPherson Area Transit Oriented Development Plan | FY 2012 | FY 2012 | 80000 | Economic Development | ARC - LCI Implementation Grant | RFP consultant selection in progress.
Pursue Opportunity Zone designation for the Corridors TAD area | FY 2011 | FY 2012 | 0 | Economic Development | N/A | Urban Redevelopment Plan completed and application submitted in FY 2011. DCA required additional data. Revised info to be submitted in August 2011.
Continue to pursue Fulton County BOE approval of Corridors TAD | FY 2011 | FY 2012 | 20000 | Economic Development/Legal | General Fund | Staff continues to work with outside Counsel on completing the BOE application and meeting with BOE management. Application to be submitted by fall 2011
Focus on Commons Redevelopment Implementation | FY 2011 | FY 2016 | $200,000 - $5 million | Economic Development/BIDA/City/Legal/CMO | General Fund/TAD/LCI Transportation funds/other grants | Completed ULI TAP Report in 2011. Staff is developing a MOU between City and BIDA for implementation. Staff is actively recruiting an anchor tenant.
Continue tourism promotion and increasing hotel occupancy through Hotel Tax Committee management and partnership with ACVB | FY 2011 | FY 2017 | 7000000 | Economic Development/Legal/CMO/Finance/ACVB | Hotel Tax | New 8% Hotel Tax rate effective June 2011. Staff and ACVB have initiated promotional materials and recruiting strategies which will continue and expand. Annual activity (contract thru FY 2013) $1.4million
Develop general incentive procedure for new business recruitment and existing business expansion | FY 2011 | FY 2012 | 0 | Economic Development/Power/Public Works/P&Z | General Fund | Procedure developed and approved for large prospect in 2011. Staff will continue to refine moving forward.
East Point Street and West Cleveland Avenue streetscape and pedestrian improvements | FY2012 | FY2017 | 4800000 | Econ.Dev./Planning & Zoning/ Public Works/GDOT/MARTA | ARC- LCI Transportation Grant/City | Projects were identified in LCI PLan. Applications due to ARC in September 2011. 80% Federal-$3,840,000 and 20% Local-$960,000
Continue Friday Night Flicks Outdoor Movie Series Equipment | FY2011 | Ongoing | 10000 | Economic Development | General Fund/Sponsors | Program started in fall 2010. Monthly movies would run April-October.
Establish a Façade Grant Program | FY 2013 | FY 2017 | 60000 | Economic Dev./BIDA | BIDA | Begin program to incentivize small cost/big impact building improvements. 50/50 match requirement. Annual activity $15,000
Establish a Small Business Revolving Loan Program | FY 2013 | Ongoing | 75000 | Economic Dev./BIDA | BIDA | Begin program to encourage local, small business development.
Establish and implement a Business Beautification/Planter Program | FY2012 | Ongoing | 10000 | Economic Development | General Fund/Sponsors/Hotel Tax | Suitable location map complete and planter estimates have been obtained. Businesses will submit application to participate.
Create expanded Business Directory/Profile & Property Listings | FY2013 | Ongoing | 8000 | Economic Development | General Fund/EPMSA | Already exists for Downtown. ED staff will work with P&Z to utilize business license data for a citywide directory.
Continue the Pick - A- Point Beautification Projects (Plantings) | FY2011 | Ongoing | 15000 | Economic Dev./EPMSA | General Fund/EPMSA/Neighborhood Associations | Program began in 2010.
Installation of Downtown bike/ped amenities (benches, trash cans, bike racks, banners) | FY2011 | Ongoing | 35000 | Economic Development | General Fund/Sponsors | Restarted in 2011 and will continue as funding permits.
City of East Point 125th Anniversary Celebration | FY2013 | FY2013 | 15000 | Econ. Dev./City Clerk/Communications Dept. | General Fund | Joint, interdepartmental effort.
Continue production of monthly Downtown East Point Newsletter | FY2011 | Ongoing | 9000 | Economic Dev./EPMSA | General Fund/ EPMSA | Started in 2009. Created, written, and designed in-house.
Continue distribution and analysis of downtown and citywide business surveys | FY 2011 | Ongoing | 1500 | Economic Development | General Fund/EPMSA | Expansion of business retention, expansion and recruitment tool used to determine work program and efforts. Can be completed and analyzed online using Surveymonkey.
Coordination of Downtown East Point Events (4th of July, Destination East Point, Taste of East Point, East Point Farmer's Market) | FY2011 | Ongoing | 436225 | Economic Dev./EPMSA | General Fund/EPMSA | Continuation of ED Department’s role in coordinating events with EPMSA. Annual activity $87,245.
Annual Business Networking Event | FY2011 | Ongoing | 5000 | Economic Dev./EPMSA | Econ. Dev./EPMSA | Started in 2010. Joint effort with EPMSA.
Annual Small Business Seminar | FY2012 | Ongoing | 5000 | Economic Development/Sponsors | General Fund/Sponsors | Continuation of business retention, expansion and attraction seminar.
Downtown East Point Website | FY2011 | Ongoing | 7500 | Economic Dev./EPMSA | General Fund/EPMSA | Updates and maintenance of www.downtowneastpoint.com
Anti-Pan Handling Campaign | FY2012 | Ongoing | 3000 | Econ. Dev./Police Department | General Fund/Police Department
Advertising in Magazines, Brochures and Online (non-Hotel Tax/tourism related) | FY2011 | FY 2016 | 100000 | Economic Development | General Fund | Annual activity $20,000
Devise and implement a capital improvement project in downtown area based on Council 2010-2011 project list | FY 2012 | FY 2017 | TBD | BIDA/Economic Development/Public Works | General Fund/MEAG/Hotel-Motel Tax
Identify potential redevelopment plan for area known as Old Fourth Ward (Willingham, Central Avenue, Eagan Par, River Park, East Washington, etc.) | FY 2012 | FY 2017 | TBD | BIDA/Economic Development/Planning & Zoning | General Fund/BIDA
Identify and implement a captial improvement project for area known as Old Fourth Ward (Willingham, Central Avenue, Eagan Par, River Park, East Washington, etc.) | FY 2012 | FY 2017 | TBD | BIDA/Economic Development/Public Works | General Fund/BIDA
Identify and implement a capital improvement project along Cleveland Avenue | FY 2012 | FY 2017 | TBD | BIDA/Economic Development/Public Works | General Fund/BIDA/EP Corridors TAD
Formalize a Summer Youth Jobs Training Program | FY 2012 | FY 2017 | 100000 | Economic Development/Parks & Recreation | General Fund | Annual activity $20,000
Total Estimated Costs |  |  | 12875225 | Note: Total estimated cost is between $9,140,225.00 - $13,940,225.00

## STWP Form-Housing
East Point Short Term Work Program
Short Term Work Program Update 2011 - 2016
Comprehensive Plan Element: | Housing
Section:
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Implementation of 50 Worst Properties Program | FY 2012 | FY 2017 | 625000 | Fire, Planning & Zoning & Police | MCT Capital fund; General Fund | Residentail & commercial vacant property program annual cost $125,000
Partnership w/Atlanta-Fulton Land Bank Authority | FY 2012 | FY 2012 | 0 | City of East Point & Atlanta-Fulton Land Bank Authority | N/A | Resource for redevelopment of vacant residential properties
Pursue allocation of Neighborhood Stabilization Funds (NSP) | FY 2012 | FY 2013 | 0 | City of East Point; Atlanta-Fulton Land Bank Authority; Fulton County |  | Resource for redevelopment of vacant residential properties
Establish loan pool to implement housing rehabilitation program for low income and senior citizens | FY 2013 | FY 2017 | 100000 | City of East Point/Fulton County | CDBG/General Fund
Develop and implement an affordable housing incentive ordinance | FY 2013 | FY 2014 | 0 | Planning & Zoning | General Fund
Investigate and implement housing rehabilitation program | FY 2013 | FY 2017 | 100000 | City of East Point/Fulton County | CDBG/General Fund
Total Estimated Costs |  |  | 825000

## STWP -NaturalCultural Resources
East Point Short Term Work Program
Short Term Work Program Update 2011 - 2016
Comprehensive Plan Element: | Natural & Cultural Resources
Section:
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
East Point Historical Society
Total Estimated Costs |  |  | 0

## STWP Form-Land Use
East Point Short Term Work Program
Short Term Work Program Update 2011 - 2016
Comprehensive Plan Element: | Land Use
Section:
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
2036 Comprehensive Plan Update | FY 2011 | FY 2012 | 143000 | Planning & Zoning | General Fund | In process
Headland-Delowe Visioning Plan | FY 2013 | FY 2013 | 50000 | Planning & Zoning | General Fund | RFP process required
Washington Road Overlay District | FY 2012 | FY 2012 | 0 | Planning & Zoning | General Fund | In-kind Service
City-initiated industrial district re-zoning | FY 2012 | FY 2013 | 0 | Planning & Zoning | General Fund | In-kind Service
South Fulton Comprehensive Transportation Plan | FY 2011 | FY 2013 | 20000 | Planning & Zoning and Public Works | General Fund | In coordination w/other South Fulton cities. Amount represents East Point's match
City-initiated commerical district re-zoning | FY 2012 | FY 2013 | 0 | Planning & Zoning | General Fund | In-kind Service
Wide-format laminating machine | FY 2013 | FY 2013 | 7500 | Planning & Zoning | General Fund | RFP process required
City-initiated residential district re-zoning | FY 2012 | FY 2013 | 0 | Planning & Zoning | General Fund | In-kind Service
Implement online services in Planning & Zoning Department | FY 2013 | FY 2014 | 1000000 | Planning & Zoning | General Fund
Greyfield Re-development Visioning Plan | FY 2013 | FY 2014 | 100000 | Planning & Zoning | General Fund | RFP process required
Offsite Records Retention Facility | FY 2013 | FY 2015 | 1000000 | Planning & Zoning | General Fund
Public Arts Program | FY 2013 | FY 2017 | 125000 | Planning & Zoning; Parks & Recreation - Cultural Enrichment Commission; Economic Development | General Fund | Resolution approved by Council 05/18/2009. Annual activity $25,000
Brownfield Re-development Visioning Plan for Lawrence Street area | FY 2013 | FY 2017 | 100000 | Planning & Zoning | General Fund | RFP process required
Develop regualtions for historic preservation | FY 2012 | FY 2014 | 0 | Planning & Zoning | General Fund | Policies to be identified in Mission 2036 comprehensive Plan update
Identify grant funding for brownfield redevelopment in Lawrence Street area | FY 2013 | FY 2017 | 0 | Planning & Zoning/Finance | General Fund
Visioning Plan and feasibility study for potential entertainment district | FY 2014 | FY 2015 | 50000 | Planning & Zoning/Economic Development | General Fund | RFP process required
Total Estimated Costs |  |  | 2595500

## STWP Form-Transportation
East Point Short Term Work Program
Short Term Work Program Update 2011 - 2016
Comprehensive Plan Element: | Transportation
Section:
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Pedestrian, bicycle and sidewalk accessibility improvements @ Paul D. West & Woodland Middle Schools | FY 2011 | FY 2013 | 375000 | Public Works; Fulton County Board of Education | GA-DOT Safe Routes to School Grant | Application submitted. Award has not been announced
Pedestrial and bicycle trail construction between U.S. 29 (Main Street) and Semmes Park -Velodrome | FY 2011 | FY2015 | 1250000 | Parks & Recreation; Public Works | GA-DOT TE Grant; General Fund | Application submitted. Award has not been announced
Main Street Scenic Byway Corridor Improvement Project (streetscape) | FY 2011 | FY 2015 | 1300000 | Planning & Zoning; Public Works | GA-DOT TE Grant; General Fund | Awaiting NTP for R-O-W acquistion
Semmes Streetscape | FY 2009 | FY 2014 | 1500000 | Public Works; GDOT | GDOT & City Match | Awaiting PFPR
16 City Gateways | FY 2012 | FY 2016 | 800000 | Public Works | City | RFP goes out in Aug 2011
Citywide Roadway Striping | FY 2012 | FY 2013 | 228000 | Public Works | City | Began Jun 2011
Citywide Pavement Management | FY 2012 | FY 2016 | 5000000 | Public Works; GDOT | GDOT & City | Pavement Management Plan will be complete Aug 2011.
Sidewalk Rehabilitation | FY 2012 | FY 2016 | 1500000 | Public Works | City | Will Begin during Fall 2011
Pedestrian facility improvements on Stone Rd., Dodson Conn., and West Taylor Ave. | FY 2012 | FY 2012 | 230208 | Public Works | MARTA | Will Begin during Fall 2011
Bus Service Between College Park, East Point, Fort McPherson and Greenbriar | FY 2013 | FY 2016 | 14550000 | MARTA | Regional Sales Tax | On unconstrained TIA project List. Sales tax referrendum goes to voters on July 11, 2012.
Unidentified Transportation Enhancements | FY 2013 | FY 2016 | 2615481 | Public Works | Regional Sales Tax | Sales tax referrendum goes to voters on July 11, 2012.
Total Estimated Costs |  |  | 29348689