## Water Supply & Treatment
East Point Short Term Work Program
Short Term Work Program Update 2011 - 2016
Comprehensive Plan Element: | Community Facilties
Section: | Water Supply & Treatment
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
| FY 2012 | FY 2013 | 250000 | Water Treatment Plant | CIP Fund
BenHill Resevoir Expansion Design | FY 2011 | FY 2013 | 373360 | CDM | Bond Fund
Market Place Elevated Water Tanks | FY 2012 | FY 2014 | 1500000 | CDM | Bond Fund
Settled Solids Facility and Clarifier Improvements | FY 2012 | FY 2014 | 65000 | Water Treatment Plant | CIP Fund | EPD Compliance
Facility Roof Improvements | FY 2012 | FY 2012 | 35000 | Water Treatment Plant | CIP Fund | Roof Leaking
WTP/Boiler System Improvements | FY 2012 | FY 2012 | 25000 | Water Treatment Plant | CIP Fund
WTP Emergency Generator for existing High Service Pumps | FY 2012 | FY 2014 | 300000 | Water Treatment Plant | CIP Fund
WTP/ Reservoir Embankment and Roadway Asphalt Paving | FY 2012 | FY 2013 | 75000 | Water Treatment Plant | CIP Fund | EPD Compliance
WTP/ Emergency Gas Engine Replacement and Improvements | FY 2012 | FY 2012 | 150000 | Water Treatment Plant | CIP Fund
Upgrade Automation Network for WTP, Pumping Stations, and Elevated Tanks | FY 2012 | FY 2016 | 250000 | Water Treatment Plant | CIP Fund | EPD Compliance
Motor Control Cabinet and Automatic Transfer Power Cabinet | FY 2013 | FY 2013 | 150000 | Water Treatment Plant | CIP Fund
Homeland Security Upgrades | FY 2012 | FY 2016 | 250000 | Water Treatment Plant | CIP Fund
WTP Chemical Feed Systems | FY 2012 | FY 2012 | 60000 | Water Treatment Plant | CIP Fund
WTP Facility Projects for Various Improvements | FY 2012 | FY 2013 | 150 | Water Treatment Plant | CIP Fund
WTP Finished Water Pump Station | FY 2012 | FY 2013 | 200000 | Water Treatment Plant | CIP Fund
Intake Raw Water Pump Station | FY 2012 | FY 2013 | 100000 | Water Treatment Plant | CIP Fund
Electrical Upgrades for Uniterrupted Power Source Network for WTP Facility | FY 2012 | FY 2012 | 25000 | Water Treatment Plant | CIP Fund
Water Laboratory Renovations | FY 2012 | FY 2014 | 250000 | Water Treatment Plant | CIP Fund
Elevated Water Tank & Booster Pump Station- Phase 1 Design | FY 2011 | FY 2011 | 378000 | CDM | Bond Fund | 85% Complete
2" and 4" Water Main Replacement Design Contract 1 | FY 2011 | FY 2011 | 444613 | CDM- Shaw E&I | Bond Fund | 80% Complete
2" and 4" Water Main Replacement Design Contract 2 | FY 2011 | FY 2011 | 263685 | CDM- ESI | Bond Fund | 90% Complete
Campbellton Road Emergency Raw Water Main Repair;Task2 - Headland Drive Emergency Wtr Repair; Task 3- Bryant Dr Storm Drain Repair | FY 2011 | FY 2011 | 343572.45 | CDM- Ruby Collins | Bond Fund | 95% Complete
Ben Hill Dam and Reservoir Expansion | FY 2013 | FY 2014 | 3000000 | CIP / Water and Sewer Dept | Possible GEFA Grant
Dodson Dr. Booster Pump Station | FY 2013 | FY 2013 | 400000 | CIP / Water and Sewer Dept | 2006 CIP Bond
2" & 4" Water Main Replacement Phase II Construction | FY 2013 | FY 2014 | 6000000 | CIP / Water and Sewer Dept | Partial Funding 2006 CIP Bond
Redwine Rd. Elevated Storage Tank | FY 2013 | FY 2014 | 4600000 | CIP / Water and Sewer Dept | Unfunded
12" Water Main Extension Design (West End Region) | FY 2013 | FY 2014 | 366000 | CIP / Water and Sewer Dept | Unfunded
12" Water Main Extension Design (Southeast Region) | FY 2015 | FY 2016 | 148000 | CIP / Water and Sewer Dept | Unfunded
12" Water Main Extension Design (Southwest Region) | FY 2014 | FY 2015 | 135000 | CIP / Water and Sewer Dept | Unfunded
16" Water Main Extension Design (Northeast Region) | FY 2014 | FY 2015 | 767000 | CIP / Water and Sewer Dept | Unfunded
12" Water Main Extension Construction (West-End) | FY 2014 | FY 2015 | 3660000 | CIP / Water and Sewer Dept | Unfunded
12" Water Main Extension Construction (SE Region) | FY 2015 | FY 2016 | 1480000 | CIP / Water and Sewer Dept | Unfunded
12" Water Main Extension Construction (SW Region) | FY 2015 | FY 2016 | 1350000 | CIP / Water and Sewer Dept | Unfunded
16" Water Main Extension Construction (NE Region) | FY 2015 | FY 2016 | 7670000 | CIP / Water and Sewer Dept | Unfunded
Total Estimated Costs |  |  | 35064380.45

## Sewerage System & Wastewater
East Point Short Term Work Program
Short Term Work Program Update 2011 - 2016
Comprehensive Plan Element: | Community Facilties
Section: | Sewerage System & Wastewater Treatment
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Annual Flow Monitoring and Rain Gauge Services | FY 2011 | FY 2012 | 204545 | CDM- ADS | Bond Fund | 65% Complete
GIS Database Updates | FY 2011 | FY 2012 | 85000 | CDM | Bond Fund | 30% Complete
SSES Phase 1 Project- Contract 1 |  | FY 2012 | 8956832.71 | CDM | Bond Fund | 87% Complete
Welcome All Road Emergency Sewer Repair; Task 2 Cleveland Ave Emergency Swr Repair; Task 3 Jefferson Ter Emergency Swr Repair | FY 2011 | FY 2012 | 544757.4 | CDM- Ruby Collins | Bond Fund | 99% Complete
Priority Sanitary Sewer Improvements Projects- Hydraulic Modeling | FY 2011 | FY 2012 | 1334110 | CDM | Bond Fund | 96% Complete
Water and Sewer Utility cost service study and comprehensive financial plan | FY 2011 | FY 2012 | 98181 | CDM | Bond Fund | 75% Complete
Jefferson Terrace Emergency Sewer Repair- Design | FY 2011 | FY 2012 | 49000 | CDM | Bond Fund | 90% Complete
Jefferson Terrace Emergency Sewer Repair- Construction | FY 2011 | FY 2012 | 200000 | CDM- Ruby Collins | Bond Fund | 85% Complete
Sanitary Sewer Capacity Improvement Projects - Design | FY 2012 | FY 2013 | 600000 | CIP / Water and Sewer Dept | 2006 CIP Bond
Norman Berry/Glenway Sewer Upgrades | FY 2013 | FY 2014 | 5300000 | CIP / Water and Sewer Dept | Unfunded
Langford Parkway Sewer Rehabilitation | FY 2014 | FY 2014 | 500000 | CIP / Water and Sewer Dept | Unfunded
Englewood/Ivydale Sewer Upgrades | FY 2014 | FY 2015 | 2350000 | CIP / Water and Sewer Dept | Unfunded
Norman Berry/S. Martin Sewer Upgrades | FY 2013 | FY 2014 | 6800000 | CIP / Water and Sewer Dept | Unfunded
Meadow Lark Sewer Replacement | FY 2014 | FY 2015 | 7300000 | CIP / Water and Sewer Dept | Unfunded
Camp Creek Pkwy Sewer Replacement | FY 2013 | FY 2014 | 9300000 | CIP / Water and Sewer Dept | Unfunded
Warren Way/Headland Drive Sewer Rehabilitation | FY 2015 | FY 2016 | 5220000 | CIP / Water and Sewer Dept | Unfunded
Total Estimated Costs |  |  | 48842426.11

## Stormwater Management
East Point Short Term Work Program
Short Term Work Program Update 2011 - 2016
Comprehensive Plan Element: | Community Facilities
Section: | Stormwater Management
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Pearl Street Stormwater Improvements Project (surface & water construction grant) | FY 2011 | FY 2015 | 1583200 | Public Works | Environmental Protection Agency (EPA); General Fund; CIP Fund | 2009 Earmark Grant
Palm Drive - Washington Ave Stormwater Improvements | FY 2012 | FY 2013 | 250000 | CIP / Public Works Dept | 2006 CIP Bond
3030 & 3042 Dodson Dr. Culvert Repair | FY 2012 | FY 2012 | 150000 | CIP / Public Works Dept | 2006 CIP Bond
Lester St/Spring Ave Stormwater Improvements | FY 2013 | FY 2014 | 2200000 | CIP / Public Works Dept | Unfunded
Sun Valley Stormwater Improvements | FY 2014 | FY 2015 | 780000 | CIP / Public Works Dept | Unfunded
Randall St & E. Forrest Ave Improvements | FY 2013 | FY 2014 | 500000 | CIP / Public Works Dept | Unfunded
Jim's Creek Stormwater Improvements | FY 2014 | FY 2016 | 1850000 | CIP / Public Works Dept | Unfunded
N. Martin Street Catch Basin Replacement | FY 2013 | FY 2013 | 50000 | CIP / Public Works Dept | Unfunded
N. Martin St Regional Storage Project | FY 2014 | FY 2015 | 2500000 | CIP / Public Works Dept | Unfunded
Calhoun Ave Pipe Replacement | FY 2014 | FY 2014 | 650000 | CIP / Public Works Dept | Unfunded
South River Tributary Improvements | FY 2015 | FY 2016 | 4000000 | CIP / Public Works Dept | Unfunded
Norman Berry Drive Pipe Replacement | FY 2015 | FY 2016 | 2500000 | CIP / Public Works Dept | Unfunded
Maria Head Terrace Berm Construction | FY 2015 | FY 2016 | 176000 | CIP / Public Works Dept | Unfunded
Georgia Power Pond | FT 2014 | FY 2015 | 250000 | CIP / Public Works Dept | Unfunded
Meadow Lark Lane Pipe Replacement | FY 2015 | FY 2016 | 64000 | CIP / Public Works Dept | Unfunded
Grove Avenue Pipe Replacement | FY 2015 | FY 2016 | 50000 | CIP / Public Works Dept | Unfunded
Total Estimated Costs |  |  | 17553200

## Solid Waste Management
East Point Short Term Work Program
Short Term Work Program Update 2011 - 2016
Comprehensive Plan Element: | Community Facilities
Section: | Solid Waste Management
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
10 -Year Solid Waste Management Plan Development | FY 2011 | FY 2012 | 36000 | Public Works |  | Plan currently being developed by consultant
Total Estimated Costs |  |  | 36000

## East Point Power
East Point Short Term Work Program
Short Term Work Program Update 2011 - 2016
Comprehensive Plan Element: | Community Facilities
Section: | East Point Power
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Install underground utilities along Main Street | FY 2013 | FY 2014 | TBD | East Point Power | Unfunded
Install underground utilities along Washington Road | FY 2014 | FY 2015 | TBD | East Point Power | Unfunded
Install underground utilities along Cleveland Avenue | FY 2015 | FY 2016 | TBD | East Point Power | Unfunded
Adding Breaker at Lakemont Substation | FY2012 | FY2012 | 70000 | East Point Power | Elec. Enterprise Fund | Capacity Increase
Pole/Inspection/Treatment | FY2012 | FY 2012 | 75000 | East Point Power | Elec. Enterprise Fund | Infrastructure Improvement
Tree Trimming (Contracted) | FY2012 | FY 2015 | 570000 | East Point Power | Elec. Enterprise Fund | Power outage/Reduction annual cost $190,000
Re-conductor Ben Hill Circuits | FY2013 | FY2014 | 250000 | East Point Power | Elec. Enterprise Fund | Replace Old Infrastructure
Total Estimated Costs |  |  | 965000

## General Government
East Point Short Term Work Program
Short Term Work Program Update 2011 - 2016
Comprehensive Plan Element: | Community Facilties
Section: | General Government
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Municipal Complex Development Team Creation | FY 2012 | FY 2012 | 2000000 | City Manager's Office | Hotel/Motel Tax, General Fund, MCT | RFP consultant selection in process
Customer Care Department Renovations | FY 2011 | FY 2012 | 100000 | City Manager's Office | General Fund | Invitation to Bid in process
Municipal Complex Design & Construction | FY 2012 | FY 2015 | 21000000 | City Manager's Office | Hotel/Motel Tax, General Fund, MCT | RFP consultant selection in process
Media/Cable Station Upgrades (server, camera, media teleprecense system) | FY 2012 | FY 2012 | 35000 | Communications | MCT Capital Funds
CAD upgrade/Conversion | FY 2012 | FY 2012 | 400000 | Information Technology | MCT Capital Funds
Upgrade audio/visual equipment | FY 2012 | FY 2012 | 70000 | Municipal Court | MCT Capital Funds
Courtroom Improvements | FY 2012 | FY 2012 | 46000 | Municipal Court | MCT Capital Funds
Backflow Program | FY 2012 | FY 2012 | 690120 | Meter Services -4446 | CIP Fund
Water Meter Program | FY 2012 | FY 2012 | 105635 | Meter Services -4446 | CIP Fund
Acquisition and implementation of new Scheduling and Force Management software | FY 2012 | FY 2013 | TBD | Customer Care Division | General Fund | work force management software to more effective manage, monitor and schedule employees (especially useful when dealing with multiple shifts)
Creation of on-line Knowledge Base | FY 2012 | FY 2013 | TBD | Customer Care Division | General Fund | on-line database available to customers that allows them to get specific information about their meters, how to calculate consumption, and other valuable information without having to necessarily speak to an associate.
Updating of Customer Care Procedures and Polices Manual | FY 2012 | FY 2013 | TBD | Customer Care Division | General Fund
Dedicated collections department | FY 2013 | FY 2014 | TBD | Customer Care Division | General Fund | Dedicated in house group of agents that solely manage the collections on utility accounts.
Fully integrated AMR (Automated Meter Response) system | FY 2013 | FY 2016 | TBD | Customer Care Division | General Fund | In process
Implementation of on-line Customer Service Chat Feature | FY 2013 | FY 2013 | TBD | Customer Care Division | General Fund | Online chat feature to better service customers.
Total Estimated Costs |  |  | 24446755

## Recreational Facilities
East Point Short Term Work Program
Short Term Work Program Update 2011 - 2016
Comprehensive Plan Element: | Community Facilties
Section: | Recreational Facilities & Services
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Woodland Aquatic Recreation Center design & construction (30,000sf). Currently, an aquatic center an recreation complex has been proposed for Ward C & D adjacent to Woodland Middle School. Such a facility has the potential to provide any number of community amenities. General cost estimates are provided for financing this facility for a period of 25 years. | FY 2012 | FY 2014 | 15000000 | Parks & Recreation | General Fund; Hotel/Motel Tax; MCT; GOB | per Parks & Recreation 2011-2020 Master Plan. Amortized over 25 years with annual payments of $800,000.00
Park Land Acquisition (8 sites) | FY 2012 | FY 2017 | 3150000 | Parks & Recreation | General Fund; MCT Funds; and GOB | per Parks & Recreation 2011-2020 Master Plan. Annual activity of $630,000.00.
Jefferson Recreation Center Improvements | FY 2012 | FY 2012 | 300000 | Parks & Recreation | MCT | per Parks & Recreation 2011-2020 Master Plan.
Capital Maintenance Budget | FY 2012 | FY 2017 | 2500000 | Parks & Recreation | General Fund; MCT Funds | per Parks & Recreation 2011-2020 Master Plan. Annual activity of $500,000.00.
Construction South Commerce Park | FY 2013 | FY 2013 | 700000 | Parks & Recreation | General Fund; LWCF; MCT & GOB | per Parks & Recreation 2011-2020 Master Plan
Master Plans for Connally Nature Center | FY 2013 | FY 2014 | 1275000 | Parks & Recreation | General Fund; LWCF; MCT & GOB | per Parks & Recreation 2011-2020 Master Plan. Annual activity of $637,500.00.
Renovation Smith-Taylor Park | FY 2013 | FY 2013 | 1600000 | Parks & Recreation | General Fund; LWCF; MCT & GOB | per Parks & Recreation 2011-2020 Master Plan
Design & Construct Park @ Redwine Road/Desert Drive | FY 2015 | FY 2017 | 2400000 | Parks & Recreation | General Fund; MCT & GOB | per Parks & Recreation 2011-2020 Master Plan. Annual activity of $1,200,000.00.
Design greenway for Headland Drive | FY 2015 | FY 2015 | 276000 | Parks & Recreation | General Fund; MCT & GOB | per Parks & Recreation 2011-2020 Master Plan
Egan Park Master Plan | FY 2015 | FY 2015 | 325000 | Parks & Recreation | General Fund; MCT & GOB | per Parks & Recreation 2011-2020 Master Plan
Georgia Sports Complex "Regional Park Concept" | FY 2016 | FY 2017 | 3000000 | Parks & Recreation | General Fund; Hotel/Motel Tax; GOB | per Parks & Recreation 2011-2020 Master Plan. Annual activity of $1,500,000.00.
Design & construct Womack Park | FY 2016 | FY 2017 | 510000 | Parks & Recreation | General Fund; MCT & GOB | per Parks & Recreation 2011-2020 Master Plan
Headland Drive Greenway | FY 2016 | FY 2017 | 276000 | Parks & Recreation | General Fund; MCT & GOB | per Parks & Recreation 2011-2020 Master Plan
Sykes Park Construction | FY 2016 | FY 2017 | 1200000 | Parks & Recreation | General Fund; MCT; LWCF & Hotel/Motel Tax | per Parks & Recreation 2011-2020 Master Plan. Annual activity of $600,000.00.
Washington Road Park | FY 2016 | FY 2017 | 670000 | Parks & Recreation | General Fund; MCT & GOB | per Parks & Recreation 2011-2020 Master Plan. Annual activity of $335,000.00.
Total Estimated Costs |  |  | 33182000

## Public Safety-Fire
East Point Short Term Work Program
Short Term Work Program Update 2011 - 2016
Comprehensive Plan Element: | Community Facilties
Section: | Public Safety Facilities & Services - Fire Rescue Department
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
EPFRD Staffing Considerations
Fire Operations personnel to reduce annual overtime budget | FY 2013 | FY 2018 | 940000 | Fire Rescue Department | General Fund | Research & Development
Create EMS Coordinator (Captain) position | FY 2013 | FY 2018 | 375000 | Fire Rescue Department | General Fund | Research & Development
Create Paramedic Instructor Position | FY 2013 | FY 2018 | 275000 | Fire Rescue Department | General Fund | Research & Development
EPFRD Service Programs
Reduce the number of fires and fire deaths through target public education programs | FY 2012 | FY 2017 | 1000000 | Fire Rescue Department | Federal Grant | Federal Evaluation Process
Requirements for Accreditation Process | FY 2013 | FY 2018 | 25000 | Fire Rescue Department | General Fund | Research & Development
Develop an Education Incentive for firefighters w/college credits | FY 2013 | FY 2018 | 560000 | Fire Rescue Department | General Fund | Research & Development
Provide support for Annual Community Health & Safety Fair Program | FY 2012 | FY 2017 | 125000 | Fire Rescue Department | Grant/General Fund | Implementing Annually @ cost of $25,000
Provide support for Annual Be Cool about Fire Safety Program | FY 2012 | FY 2017 | 100000 | Fire Rescue Department | Grant/General Fund | Implementing Annually @ cost of $20,000
Provide Fans for Annual Senior Fan Give-A-Way Program | FY 2012 | FY 2017 | 250000 | Fire Rescue Department | Grant/General Fund | Implementing Annually @ cost of $50,000
Create a CERT to prepare citizens to respond to disasters in our local community | FY 2012 | FY 2018 | 20000 | Fire Rescue Department | Federal Grant | Research & Development
Create a Fire Corp Program to prepare citizens to aide in fire service support functions | FY 2012 | FY 2017 | 25000 | Fire Rescue Department | Federal Grant | Research & Development
Procure Child Safety Seat equipment for CSSP | FY 2012 | FY 2017 | 20000 | Fire Rescue Department | Grant/General Fund | Implementing Phase I
Provide Community Deputy Fire Marshal Training | FY 2012 | FY 2017 | 50000 | Fire Rescue Department | Grant/General Fund | Implementing Annually @ cost of $10,000
Provide CPR/AED Training Classes to Community | FY 2012 | FY 2017 | 37500 | Fire Rescue Department | General Fund | Implementing Annually @ cost of $7,500
Create a Fire Cadet Program to prepare students for future career fire service employment | FY 2013 | FY 2018 | 125000 | Fire Rescue Department | Federal Grant | Research & Development
Develop a partnership w/marketing agencies and local media to improve relationships & public image | FY 2012 | FY 2017 | 100000 | Fire Rescue Department | Grant/General Fund | Research & Development
EPFRD Facilities Improvement Plan
Fire Stations # 2 & #4 Design & Renovation Improvements (5 Year CIP) | FY 2012 | FY 2017 | 175000 | Fire Rescue Department | Grant/General Fund | Implementing Phase I
Fire Station # 3 Erosion Design & Construction Costs ( 5 year CIP) | FY 2012 | FY 2017 | 500000 | Fire Rescue Department | General Fund/Inkind | Implementing Phase I
Fire Administration Office Facility (Municipal Complex Design & Construction) (5 year CIP) | FY 2012 | FY 2013 | 1110000 | Fire Rescue Department | Hotel/Motel Tax, General Fund, MCT | Research & Development
Fire Station # 2 Design & Construction for Replacement (5 year CIP) | FY 2013 | FY 2014 | 6000000 | Fire Rescue Department | Grant/General Fund | Research & Development
Fire Station # 4 Design & Construction for Replacement (5 year CIP) | FY 2013 | FY 2014 | 6000000 | Fire Rescue Department | Grant/General Fund | Research & Development
Create a Multi-Agency Public Safety Emergency Operations Center (EOC) Facility (5 year CIP) | FY 2013 | FY 2014 | 2000000 | Fire Rescue Department | Grant/General Fund | Research & Development
Create a Multi-Agency Public Safety Training Facility (5 Year CIP) | FY 2013 | FY 2014 | 2000000 | Fire Rescue Department | Grant/General Fund | Research & Development
EPFRD Equipment
Implement Vehicle Replacement Program (VRP) | FY 2012 | FY 2017 | 150000 | Fire Rescue Department | General Fund | Research & Development
Implement Automatic Vehicle Locator Sys (AVLS) | FY 2013 | FY 2018 | 25000 | Fire Rescue Department | Federal Grant | Research & Development
Replace Rescue Units w/Transporting Rescue Units | FY 2012 | FY 2013 | 650000 | Fire Rescue Department | General Fund | Research & Development
Replace Reserve Ladder Unit #1 | FY 2014 | FY 2015 | 1500000 | Fire Rescue Department | General Fund | Research & Development
Provide second set of PPE for all Firefighter Personnel | FY 2012 | FY 2015 | 160000 | Fire Rescue Department | General Fund | Invitation to Bid in process
Replace Cardiac Monitors | FY 2012 | FY 2017 | 60000 | Fire Rescue Department | General Fund | Research & Development
Procure ACLS equipment for paramedic program | FY 2012 | FY 2017 | 200000 | Fire Rescue Department | General Fund | Research & Development
Replace Hurst Tools & Equipment | FY 2012 | FY 2017 | 100000 | Fire Rescue Department | Grant/General Fund | Research & Development
Replace Fire Hose | FY 2012 | FY 2017 | 300000 | Fire Rescue Department | General Fund | Invitation to Bid in process
Replace Fire Safety House | FY 2013 | FY 2017 | 200000 | Fire Rescue Department | Grant/General Fund | Research & Development
Fire Extinguisher Simulator | FY 2013 | FY 2017 | 20000 | Fire Rescue Department | Grant/General Fund | Research & Development
EPFD Emergency Prepardness
Disaster Prepardness Simulator | FY 2013 | FY 2017 | 50000 | Fire Department | Grant/General Fund | Research & Development
Total Estimated Costs |  |  | 25227500

## Public Safety-Police
East Point Short Term Work Program
Short Term Work Program Update 2011 - 2016
Comprehensive Plan Element: | Community Facilties
Section: | Public Safety Facilities & Services - Police
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Composite Drawing Software | FY 2013 | FY 2013 | 9500 | East Point Police-Support Services Division | General Fund
Krime Site Imager | FY 2013 | FY 2013 | 18950 | East Point Police-Support Services Division | General Fund
Jail Upgrade Electrical System | FY 2013 | FY 2013 | 40000 | East Point Police-Support Services Division | General Fund
Jail Computer and Monitoring System | FY 2014 | FY 2014 | 100000 | East Point Police-Support Services Division | General Fund
Jail Plumbing Upgrade | FY 2014 | FY 2014 | 60000 | East Point Police-Support Services Division | General Fund
Jail Camera System | FY 2014 | FY 2014 | 100000 | East Point Police-Support Services Division | General Fund
Total Estimated Costs |  |  | 328450

## Hospitals & Other Public Health
East Point Short Term Work Program
Short Term Work Program Update 2011 - 2016
Comprehensive Plan Element: | Community Facilties
Section: | Hospitals & Other Public Health Facilities
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
South Fulton Medical Center |  |  |  | Tenet Healthcare |  | Facilities are located in East Point, no funding required from the City
Grady Health Clinic |  |  |  | Fulton County |  | Facilities are located in East Point, no funding required from the City
Total Estimated Costs |  |  | 0

## Libraries & Cultural Facilities
East Point Short Term Work Program
Short Term Work Program Update 2011 - 2016
Comprehensive Plan Element: | Community Facilties
Section: | Libraries & Other Cultural Facilities
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
East Point Library |  |  |  | Fulton County |  | Facilities are located in East Point only, no funding required from the City
Bowden Senior Multi-Purpose Facility |  |  |  | Fulton County |  | Facilities are located in East Point only, no funding required from the City
Total Estimated Costs |  |  | 0

## Educational Facilities
East Point Short Term Work Program
Short Term Work Program Update 2011 - 2016
Comprehensive Plan Element: | Community Facilties
Section: | Educational Facilities
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
|  |  |  | Fulton County Board of Education |  | Facilities are located in East Point only, no funding required from the City
Conley Hills Elementary School |  |  |  | Fulton County Board of Education |  | Facilities are located in East Point only, no funding required from the City
Hamilton E. Holmes Elementary School |  |  |  | Fulton County Board of Education |  | Facilities are located in East Point only, no funding required from the City
Mt. Olive Elemetary School |  |  |  | Fulton County Board of Education |  | Facilities are located in East Point only, no funding required from the City
Parklane Elementary School |  |  |  | Fulton County Board of Education |  | Facilities are located in East Point only, no funding required from the City
Paul D. West Middle School |  |  |  | Fulton County Board of Education |  | Facilities are located in East Point only, no funding required from the City
Woodland Middle School |  |  |  | Fulton County Board of Education |  | Facilities are located in East Point only, no funding required from the City
Tri-Cities High School |  |  |  | Fulton County Board of Education |  | Facilities are located in East Point only, no funding required from the City
Point University (formerly Atlanta Christian College) |  |  |  | Point University |  | Facilities are located in East Point only, no funding required from the City
Total Estimated Costs |  |  | 0