## STWP Form-Transportation
Fulton County Short Term Work Program
Short Term Work Program Update 2007-2011
Comprehensive Plan Element: | Transportation
Section:
Project Name | Type of Project | Estimated Project Start Date | Estimated Project End Date | Project/ Activity Estimated Cost | Responsible Department/Agency | Funding | Status/Remarks | Districts
T114 SR 70/Fulton Industrial Boulevard | Widening | 1992-12-01 | 2008-12-31 | 22720057 | GDOT | GDOT/Fulton County | Construction | District 5
T009 Fairburn Road - Phase I | Upgrade | 1998-06-01 | 2009-01-30 | 1299436 | Fulton County | GDOT/Fulton County | Design | District 7
T019 Buffington Road - Phase I | Upgrade | 2005-04-01 | 2007-01-01 | 2942922 | Fulton County | GDOT/Fulton County | Construction | District 7
T040 Cochran Mill Road over Pea Creek | Bridge Replacement | 2004-06-01 | 2009-07-30 | 886000 | Fulton County | GDOT/Fulton County | Design | District 7
T115 South Fulton Scenic Byway - Phase I | Multi-use Trail | 2005-07-01 | 2009-07-01 | 2442110 | Fulton County | GDOT/Fulton County | Design | District 7
T123 Will Lee Road | Sidewalk/Bicycle Route | 2003-07-01 | 2008-07-23 | 2925927 | Fulton County | GDOT/Fulton County | Pre-Construction | District 7
T162 Sandtown Pedestrian Network | Sidewalk Improvement | 2005-06-01 | 2009-04-24 | 9948220 | Fulton County | GDOT/Fulton County | Design | District 7
T184 Off System Safety Pilot Project | Pedestrian Improvement | 2005-10-06 | 2007-12-01 | 241925 | Fulton County | GDOT/Fulton County | Design | District 7
T185 Cascade-Palmetto Road (SR 70) over Deep Creek | Bridge Replacement | 2005-06-01 | 2007-12-25 | 1688200 | Fulton County / GDOT | GDOT/Fulton County | Construction | District 7
T186 Cascade-Palmetto Road (SR 154) over Bear Creek | Bridge Replacement | 2005-06-01 | 2008-09-18 | 1133959 | Fulton County / GDOT | GDOT/Fulton County | Design | District 7
T188 Buffington Road - Phase II | Upgrade | 2005-09-01 | 2009-10-30 | 3494890 | Fulton County | GDOT/Fulton County | Design | District 7
T193 Fairburn Road - Phase II | Road Upgrade Improvement | 1998-06-01 | 2009-01-03 | 2003906 | Fulton County | GDOT/Fulton County | Design | District 7
T208 SR 154 (Cascade-Palmetto Hwy) at Wilkerson Mill Road | Intersection Improvement | 2007-07-30 | 2009-12-01 | 2190000 | GDOT | GDOT/Fulton County | RFP | District 7
T209 SR 279 (Old National Hwy) Transit-Oriented Development | Sidewalk Improvement | 2007-07-30 | 2010-01-18 | 1650000 | Fulton County / College Park | GDOT/Fulton County | RFP | District 7
T210 SR 14 (South Fulton Parkway) Access Management Plan | Study | 2007-07-30 | 2010-12-12 | 400000 | Fulton County / GDOT | GDOT/Fulton County | RFP | District 7
T211 SR 279 (Old National Highway) ATMS | Arterial Communication | 2007-07-30 | 2010-01-18 | 800000 | Fulton County / GDOT | GDOT/Fulton County | RFP | District 7
T212 Oakley Industrial Boulevard | Road Upgrade Improvement | 2005-09-01 | 2008-12-01 | 4520000 | Fulton County | GDOT/Fulton County | Design | District 7
T213 SR 154 (Cascade-Palmetto Hwy) at Cedar Grove Road/Ridge Road | Intersection Improvement | 2005-12-01 | 2009-12-01 | 1480000 | GDOT | GDOT/Fulton County | RFP | District 7
T215 Campbellton Road at Randolph Elementary School | Intersection Improvement | 2005-12-01 | 2007-06-15 | 909568 | Fulton County | Fulton County | Construction | District 7
T216 Cascade Road Corridor Study | Traffic Signal and Safety Ops | 2006-06-01 | 2007-06-01 | 108290 | Fulton County | Fulton County | Under Study | District 7
T227 Butner Road over Camp Creek Parkway | Bridge Replacement | 2007-07-30 | 2009-05-30 | 1800000 | Fulton County | Fulton County | RFP | District 7
T226 Oakley Road over Broadnax Creek | Bridge Replacement | 2007-12-01 | 2009-12-01 | 397600 | Fulton County | Fulton County | RFP | District 7
T234 Stonewall Tell Road over Camp Creek | Bridge Replacement | 2005-10-01 | 2007-04-30 | 1940595 | Fulton County | Fulton County | Construction | District 7
T237 SR70/(Cascade-Palmetto Hwy.) over Camp Creek | Bridge Replacement | 2003-08-01 | 2007-12-01 | 2995000 | Fulton County / GDOT | GDOT/Fulton County | Design | District 7
Total Estimated Costs |  |  |  | 70918605

## STWP Form-NaturalCultural Res
Fulton County Short Term Work Program
Short Term Work Program Update 2007-2011
Comprehensive Plan Element: | Natural & Cultural Resources
Section:
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Review/approve EnvironmentalSite Analysis reports included in zoning applications | April 2007 | December 2011 | In-Kind | Environment and Community Development | Fulton County | Ongoing; Environmental Site Analysis report is required for all rezoning and use permit application
Environmental Justice | June 2007 | June 2008 | In-Kind | Environmental and Community Development, Economic Development | Fulton County | Ongoing; Develop additional environmental requirements for proposed development adjacent to environmental stressors
Fulton Industrial Boulevard Redevelopment Project | April 2007 | April 2008 | In-Kind | Environment and Community Development, Economic Development | Fulton County | Ongoing; Provide environmental expertise on redevelopment project
Expand hazardous waste education program | April 2007 | April 2008 | In-Kind | Public Works | Fulton County | Ongoing
Sponsor a Hazardous Waste Amnesty Day | May 2007 | December 2008 | In-Kind | Public Works, Fire Department | Fulton County | Ongoing
Institute recycling program/education in South Fulton | May 2007 | December 2008 | In-Kind | Public Works, General Services | Fulton County | Ongoing
Seek WaterFirst designation with Georgia Department of Community Affairs | May 2007 | December 2008 | In-Kind | Public Works | Fulton County | Ongoing
Coordinate cleanup of Fulton Industrial corridor | May 2007 | December 2008 | In-Kind | Public Works, local businesses | Fulton County
Total Estimated Costs |  |  | 0

## STWP Form-Housing
Fulton County Short Term Work Program
Short Term Work Program Update 2007-2011
Comprehensive Plan Element: | Housing
Section:
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Kensington Heights - Welcome All Road; 95 single family lots | 2005-02-01 | 2007-06-01 | 15200000 | Fulton County Housing and Community Development | HOME funds, Wachovia & Brand Banking Co. | CHDC loan=$384,300 for land acquisition provided inclusion of low to moderate income housing set aside. 50% complete
Ruby Creek - DeMooney Road; 25 single family lots | 2004-01-01 | 2008-04-01 | 5000000 | Fulton County Housing and Community Development | HOME funds, & Southern Community Bank | CHDC loan=$510,000 for land acquisition provided inclusion of low to moderate income housing set aside. In progress of infrastructure
Victoria Estates - Virlyn B. Smith Pkwy; older adult community, 27 single family homes | 2005-05-01 | 2007-06-01 | 4250000 | Fulton County Housing and Community Development | HOME funds & Southern Community Bank | CHDC loan=$340,000 for land acquisition provided inclusion of low to moderate income housing set aside.
Providence Glen - Old National Hwy; 60 Single family | 2004-01-01 | 2006-12-01 | 10500000 | Fulton County Housing and Community Development | HOME funds & Regions Bank | CHDC loan=$399,756 for land acquisition and soft cost. 90% complete
Nelson McGee - Old National Hwy; 29-unit condominium for age 55 and older | 2004-10-01 | 2007-07-01 | 4950000 | Fulton County Housing and Community Development | HOME funds & BB & T. | CHDC loan=$399,000 for land acquisition and interest reserve account required by bank for infrastructure loan
Harmony Village - Flat Shoals Road; 47-units | 2005-07-01 |  | 7500000 | Fulton County Housing and Community Development | HOME funds & Flag Bank | FORECLOSED
Stonewall Village - Stonewall Tell Road; 390-units for age 55 and older | 2006-08-01 | 2008-12-01 | 35000000 | Fulton County Housing and Community Development/Fulton County Human Services | HOME funds, Low Income Tax Credits & Bond Financing
Sweetwater Creek - a mixed income community with 34 single family homes | 2006-05-01 | 2008-12-01 | 7990000 | Fulton County Housing and Community Development | HOME Funds & private financing | CHDO Grant $525,000
Fulton County Housing Rehabilitation | 2007-01-01 | 2007-12-01 | 550000 | Fulton County Housing and Community Development | HOME Funds
Home Owner Assistance Program & American Dream | 2007-01-01 | 2007-12-01 | 600000 | Fulton County Housing and Community Development | HOME Funds & ADDI
Total Estimated Costs |  |  | 91540000

## STWP Form-Economic Development
Fulton County Short Term Work Program
Short Term Work Program Update 2007-2011
Comprehensive Plan Element: | Economic Development
Project/Activity Description | Estimated Project Start Date | Estimated Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Fulton County Business Improvement Loan Program (BILP) | 2005-01-01 | 2008-12-01 | 173000 | Fulton County | CDBG
Fulton County Business Improvement Loan Program (BILP) Program Income | 2005-01-01 | 2008-12-01 | 100000 | Fulton County | CDBG
Women's Economic Development Agency | 2005-01-01 | 2008-12-01 | 46500 | Fulton County | CDBG
Godby Road Business Park | 2005-01-01 | 2009-12-01 | 100000 |  |  | Matching planning funds
International Village @ South Fulton Pkwy | 2006-01-01 | 2008-12-01 | 5100000 |  | Pending
South Fulton Technology Park Expansion | 2005-06-01 | 2008-12-01 | 300000 |  | Pending
Chattahoochee Hill Country Land Bank - Phase II | 2005-06-01 | 2008-12-01 | 150000 |  | Pending
Increase population of Atlanta's Central Business District (to 50,000 people) | 2004-01-01 | 2009-12-01 | 10000
Mt. Carmel Commercial / Campbellton Road - Phase I | 2004-01-01 | 2008-12-01 |  |  | Bond financing | Pending
Eastside Tax Allocation District - Phase II | 2005-06-01 | 2008-12-01 | 5000 |  | Economic Development | Pending
Peachtree Bottom Project | 2006-01-01 | 2008-12-01 | 5000 |  | Development Authority of Fulton County | Pending
Georgia State University Expansion | 2005-06-01 | 2008-12-01 |  |  | Development Authority of Fulton County | Pending
ARCO Office Park @ South Fulton Pkwy | 2004-01-01 | 2008-12-01 | 100000 |  | Development Authority of Fulton County | Pending
South Fulton office development | 2004-01-01 | 2008-12-01 | 13600000 |  | Pending | Pending
Nano-Technology Program | 2004-01-01 | 2008-12-01 | 10000000 |  | World Venture Capitalist Assoc. | Pending
Total Estimated Costs |  |  | 29689500

## STWP Form-Land Use
Fulton County Short Term Work Program
Short Term Work Program Update 2006-2010
Comprehensive Plan Element: | Land Use
Project/Activity Description | Estimated Project Start Date | Estimated Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
Amendment to Zoning Resolution Article 33 | 2004-06-01 | 2007-12-01 | In-kind | Environment & Community Developemnt | Fulton County
Sandtown LCI Implementation | 2006-06-01 | 2007-12-01 |  | Public Works | Fulton County/State/Federal
Old National LCI Implementation | 2005-04-01 | 2007-12-01 | 1650000 | Public Works | Fulton County/State/Federal | Included in ARC 2005-2010 Transportation Improvement Program
Fulton Industrial Overlay District | 2007-05-01 | 2007-12-01 | In-kind | Environment & Community Development |  | Not Programmed
Amend all Overlay Districts in Zoning Resolution | 2007-01-01 | 2009-01-01 | In-kind | Environment & Community Development | Fulton County
Annual Population Update | 2006-04-01 | 2006-10-01 | In-kind | Environment & Community Development | Fulton County
Fulton Industrial Redevelopment Plan | 2006-04-01 | 2007-12-01 | In-kind | Environment & Community Development | Fulton County
Land Use Map Amendment | 2006-04-02 | 2006-12-02 | In-kind | Environment & Community Development | Fulton County
Total Estimated Costs |  |  | 1650000

## STWP Form-Community Facilities
Fulton County Short Term Work Program
Short Term Work Program Update 2007-2011
Comprehensive Plan Element: | Community Facilties
Section: | Water Supply & Treatment
Project/Activity Description | Estimated Project Start Date | Estimated Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
City of Mountain Park - Waterline (Lake Cherful) | 2007-01-01 | 2008-03-01 | 60000 | Fulton County | CDBG
City of Roswell - Waterline (Charles Pl./Rocky CK.) | 2007-01-01 | 2008-03-01 | 130784 | Fulton County | CDBG
City of Roswell - Dams & Mills (Vickery Creek Park) | 2007-01-01 | 2008-03-01 | 50836 | Fulton County | CDBG
City of Mountain Park - Waterline (Lake Cherful) | 2008-01-01 | 2009-03-01 | 50000 | Fulton County | CDBG
City of Roswell - Waterline (Charles Pl./Rocky CK.) | 2008-01-01 | 2009-03-01 | 109216 | Fulton County | CDBG
City of Roswell - Stream Bank Improvements | 2008-01-01 | 2009-03-01 | 150000 | Fulton County | CDBG
Total Estimated Costs |  |  | 550836
Comprehensive Plan Element: | Community Facilties
Section: | Sewerage System & Wastewater Treatment
Project/Activity Description | Estimated Project Start Date | Estimated Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
City of Fairburn - Sanitary Sewer Improvements | 2007-01-01 | 2008-03-01 | 60000 | Fulton County | CDBG
City of Fairburn - Sanitary Sewer Improvements | 2008-01-01 | 2009-03-01 | 50000 | Fulton County | CDBG
Total Estimated Costs |  |  | 110000
Comprehensive Plan Element: | Community Facilties
Section: | Stormwater Management
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
City of Union City - Sewer & Sidewalk (Lakeside Dr) | 2007-01-01 | 2008-03-01 | 60000 | Fulton County | CDBG
Total Estimated Costs |  |  | 60000
Comprehensive Plan Element: | Community Facilties
Section: | Public Safety Facilities & Services
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
In His GREAT Name (Facility Improvements) | 2007-01-01 | 2007-12-01 | 40000 | Fulton County | CDBG
North Fulton Charities (Facility Improvements) | 2007-01-01 | 2007-12-01 | 45250 | Fulton County | CDBG
Young Adult Guidance Center (Facility Improvements) | 2007-01-01 | 2007-12-01 | 105250 | Fulton County | CDBG
In His GREAT Name (Facility Improvements) | 2008-01-01 | 2009-12-01 | 42900 | Fulton County | CDBG
North Fulton Charities (Facility Improvements) | 2008-01-01 | 2009-12-01 | 80000 | Fulton County | CDBG
Total Estimated Costs |  |  | 313400
Comprehensive Plan Element: | Community Facilties
Section: | Recreational Facilities & Services
Project/Activity Description | Project Start Date | Project End Date | Project/Activity Estimated Cost | Responsible Department/Agency | Funding Source | Status/Remarks
City of Alpharetta (Adaptive Sports Complex) | 2007-01-01 | 2008-03-01 | 60000 | Fulton County | CDBG
City of College Park (Godby Rd. Pool) | 2007-01-01 | 2008-03-01 | 73000 | Fulton County | CDBG
City of East Point (Parks Improvements) | 2007-01-01 | 2008-03-01 | 80380 | Fulton County | CDBG
City of Hapeville (Parks Improvements) | 2007-01-01 | 2008-03-01 | 60000 | Fulton County | CDBG
City of Alpharetta (Adaptive Sports Complex) | 2008-01-01 | 2009-03-01 | 50000 | Fulton County | CDBG
City of College Park (Godby Rd. Pool) | 2008-01-01 | 2009-03-01 | 52000 | Fulton County | CDBG
City of East Point (Parks Improvements) | 2008-01-01 | 2009-03-01 | 53168 | Fulton County | CDBG
City of Hapeville (Parks Improvements) | 2008-01-01 | 2009-03-01 | 50000 | Fulton County | CDBG
City of Roswell (Waller Park Extension) | 2008-01-01 | 2009-03-01 | 115000 | Fulton County | CDBG
Total Estimated Costs |  |  | 593548

## Water CIP
Fulton County Short Term Work Program
Short Term Work Program Update 2007-2011
2007-2008 WATER CIP PROJECTS
Project Number | Project Name | Estimated Cost | Contract Amount | Project Description | Source Document(s) | Authorized Date | PM Start Date | Construction Start | Construction Complete
H065 | Water Stand-by Projects | 4968299 |  | Stand-by projects | Hydraulic Model Expansion and Calibration of the North Fulton County Water System, Metcalf & Eddy, Inc., August 2003. |  |  | Ongoing as needed
W017 | Miscellaneous Unit Price Water Lines | 3095703 |  | Construction of miscellaneous water lines throughout Fulton County | Hydraulic Model Expansion and Calibration of the North Fulton County Water System, Metcalf & Eddy, Inc., August 2003. |  |  | Ongoing as needed
W027 | North Fulton Pump Stations | 635521 |  | Design of three booster pump stations to provide increased pressure and improved flow for the North Fulton Water System (W030, W031, W032) | Hydraulic Model Expansion and Calibration of the North Fulton County Water System, Metcalf & Eddy, Inc., August 2003. |  | 2005-08-15 | Design to be completed 06/07 | 2006-12-15
W026 | North Fulton Maintenance & Operations Center | 8991083 |  | Design & Construction of the North Fulton Maintenance & Operations Center on Maxwell Rd. in Alpharetta | Fulton County Technical Services, July 2003. |  | 2004-05-03 | Design ongoing. Construction TBD | TBD
W030 | Mansell Rd. Booster Pump Construction | 2100000 |  | Construction of a 50 HP booster pump station at Mansell Road to provide increased pressure and improved flow for the North Fulton Water System. |  |  |  | 2007-09-07 | 2009-07-20
W031 | Providence Rd. Booster Pump Construction | 1900000 |  | Construction of a 75 booster pump station at Providence and Cowart Roads to provide increased pressure and improved flow for the North Fulton Water System. |  |  |  | 09/00/07 | 2009-08-06
W032 | Freemanville Rd. Water Main and Elevated Storage Tank | 9000000 |  | Construction of approximately 30,000 linear feet of 24-inch diameter water main along Freemanville Road and a 0.50 MGD elevated storage tank at Freemanville Road near Henderson Road to provide increased pressure and improved flow for the North Fulton Water System. |  |  |  | 09/00/07 | 2009-08-06
W034 | Water Main Relocations - GA DOT Reimbursement | 6000000 |  | Reimbursement to GDOT for relocation of water mains |  |  |  | Ongoing as needed
2007-2008 WATER CIP PROJECTS
Project Number | Project Name | Estimated Cost | Contract Amount | Project Description | Source Document(s) | Authorized Date | PM Start Date | Construction Start | Construction Complete
W035 | Riverside Road Water Main | 3800000 |  | Construction of approx. 10,800 LF of new water main, from 8-inch to 24-inch, along Riverside Dr between Atlanta Rd and GA-400 in the City of Roswell. |  |  |  | 06/00/07 | 05/00/08
W037 | North Fulton (West of GA-400) Storage Tanks | 5200900 |  | Construction of two 2-million gallon elevated storage tanks and related piping at a site in Northwest Roswell to improve fire protection supply. |  |  |  | 10/00/07 | 10/00/08
W038 | AFCWTP Phase 3.0 | 20000000 |  | Fulton County contribution to expansion of the Atlanta / Fulton County Water Treatment Plant. |  |  |  | Design ongoing. Construction TBD | TBD
W039 | Alpharetta Pipe Replacement | 10322000 |  | Replacement of asbestos-cement, galvanized, and PVC water pipe as well as other repairs and enhancements in excess of 40,000 feet for the Alpharetta water system. |  |  |  | Design ongoing. Construction TBD | TBD
TOTAL 2007 - 2008 WATER PROJECTS |  | 76013506 | 0

## Wastewater CIP
Fulton County Short Term Work Program
Short Term Work Program Update 2007-2011
2007 - 2008 WASTEWATER CIP PROJECTS
Project Number | Project Name | Estimated Cost | Contract Amount | Project Description | Source Document(s) | Authorized Date | PM Start Date | Construction Start | Construction Complete
I067 | Sewer Stand-by Projects | 6000000 |  | Sewer stand-by projects
S079 | Miscellaneous Sewer Line Unit Price Contracts | 3084421 |  | Construction of miscellaneous sewer lines in Fulton County
S119 | Morning Creek I & I Phase II | 4683034 |  | Inspection and repair of approx. 115 miles of sewer line in the Morning Creek Basin in South Fulton County to reduce infiltration and inflow. |  |  |  | 2005-05-31 | 06/00/07
R002 | Bell Rd. Reuse Water Main Extension Phase I | 820756 |  | Construct 5,250 feet of 20-inch DIP reuse water main from Cauley Creek WRF to the Sugar Mill Subdivision |  |  |  | 03/00/07 | 08/00/07
R004 | Bell Rd. Reuse Water Main Extension Phase II | 1407588 |  | Construction of 8,210 ft reuse water line (20-inch DIP) starting from Bell Road Phase I to Standard Club / Abbotts Bridge Rd. |  |  |  | 09/00/06 | 03/00/07
2007 - 2008 WASTEWATER CIP PROJECTS
Project Number | Project Name | Estimated Cost | Contract Amount | Project Description | Source Document(s) | Authorized Date | PM Start Date | Construction Start | Construction Complete
S105 | Wastewater System Model & Comprehensive Master Plan | 2599590 |  | A detailed computer generated hydraulic model of the wastewater collection and conveyance system using information obtained from the Survey and Inventory project (S217). The purpose is to develop a comprehensive master plan outlining the capacity and maintenance needs of the wastewater system. |  |  |  | 2005-12-12 | 2010-01-04
S106 | CMMS/CIS Billing, Development & Acquisition | 1485237 |  | Procurement, development, and implementation of a Computerized Maintenance and Management System (CMMS) and a Customer Information System (CIS) for Fulton County Public Works, Water Services Division. |  |  |  | 2006-01-10 | 2008-04-16
S107 | CMMS / CIS Billing, Software/Hardware Procurement | 2587094 |  | Procurement of software and hardware in support of Project S106 |  |  |  | 2006-08-30 | 2008-04-16
S109 | Riverside Road Pump Station Upgrade | 10490600 |  | This project involves professional architectural and engineering design services for improving the various existing functions of the pump station including odor control and an increase in firm pumping capacity of the Pump Station from 40 Millions Gallons per Day (“MGD”) to 80 MGD. The design RFP also provides for the emergency power supply of three pump stations in North Fulton. |  |  |  | Design ongoing. Construction TBD | TBD
S231 | Marsh Creek P.S. | 2000000 |  | Replace existing facility w/a new P.S |  |  |  | 03/00/09 | 03/00/10
S110 | Marsh Creek Sewer Upgrade | 4000000 |  | To upgrade and increase capacity of 14,000 feet of sewer interceptor and trunk lines in the Marsh Creek Sewer Basin. Work involves replacement of 8-inch, 12-inch, and 18-inch pipe, with 10-inch, 12-inch, 22-inch, 24-inch, and 28-inch HDPE and DIP. Replacement or rehabilitation of up to 60 manholes may be required. |  |  |  | Design on going. Construction TBD. | TBD
2007 - 2008 WASTEWATER CIP PROJECTS
Project Number | Project Name | Estimated Cost | Contract Amount | Project Description | Source Document(s) | Authorized Date | PM Start Date | Construction Start | Construction Complete
S114 | Lake Windward I & I Reduction Project | 4000000 |  | Inspection and repair of 25,500 feet of sewer line to eliminate infiltration and inflow in the Lake Windward area of the Big Creek Basin in Alpharetta / Northeast Fulton County. |  |  |  | 2006-01-31 | 2008-06-30
S115 | Johns Creek Environmental Campus | 134742941 |  | Relocation of the Johns Creek WTP to a new location on 43 acres of land bordered by Holcomb Bridge Rd and the Chattahoochee River in Northeast Fulton County. The facility will be expanded to 15 MGD capacity. The facility will use Membrane Bio-Reactor technology and will meet or exceed current advanced discharge limits and provide high quality urban reuse water to surrounding irrigation customers. |  |  |  | 2006-06-14 | 12/00/09
S119 | Morning Creek / Camp Creek Infiltration & Inflow | 1524613 |  | Inspection and repair of sewer line in the Deep Creek sewer basin in Southwest Fulton County to eliminate infiltration and inflow. |  |  |  | 2006-11-22 | 2008-02-14
S217 | Survey & Inventory | 7957783 |  | Project to survey Fulton County's water and wastewater systems. |  |  |  | 2003-03-25 | 2008-03-08
S218 | Sewer Repair Group Phase I | 1998300 |  | Phase I of project to repair sewers |  |  |  | Ongoing
S219 | Brookfield Country Club Sewer Lining | 800216 |  | Line approximately 3,000 LF of 12-inch sewer line in the Brookfield Subdivision with a cured-in-place liner to eliminate inflow and infiltration. |  |  |  | 2006-09-26 | 2007-12-19
S220 | Big Creek I & I | 3500000 |  | Inspection and repair of approx. 65 miles of sewer line to eliminate infiltration and inflow along Azalea Drive / Riverside Drive. |  |  |  | 2006-05-23 | 2008-03-03
S221 | Big Creek WRF to Cobb County RL Sutton WRF Diversion | 2000000 |  | Design and construction of 2,800 LF of 16-inch force main to transport 3.5 mgd wastewater from Riverside PS to the Little Willeo Creek P.S. / Cobb County collection system for treatment at the R. L. Sutton WRF. |  |  |  | 09/00/07 | 01/00/08
2006 - 2007 WASTEWATER CIP PROJECTS
Project Number | Project Name | Estimated Cost | Contract Amount | Project Description | Source Document(s) | Authorized Date | PM Start Date | Construction Start | Construction Complete
S223 | Azalea Road Pumping Station And Force Main Project | 700000 |  | Study to determine feasibility of reactivating Azalea Rd Pumping Station and force main |  |  |  | 2006-11-21 | 2007-12-05
S224 | Interim Capacity Additions - Big Creek WRF | 10000000 |  | Improvements to the Big Creek WRF necessary to provide approximately seven (7) million gallons per day of additional wet weather treatment capacity. |  |  |  | 09/00/06 | 01/00/09
S225 | Butterfield Lane Sewer Replacement | 600000 |  | Replacement of approximately 3,100 LF of existing 8-inch sewer in Butterfield Lane located in South Fulton and replacing it with 12-inch high density polyethylene (HDPE) using pipe bursting construction. |  |  |  | 07/00/07 | 06/00/08
S230 | Old Alabama and Lake Charles Pump Station Standby Power Generator Design and Installation | 780000 |  | Project to provide new standby power generators at Old Alabama and Lake Charles Pump Stations in North Fulton County. The work will also include electrical and mechanical upgrades for generator connections, the addition of a third submersible pump and VFD, and a 5-ton wet well hoist at Old Alabama. |  |  |  | 05/00/07 | 10/00/07
TOTAL 2006 - 2007 WASTEWATER PROJECTS |  | 207762173 | #REF!
Funding Source: Water & Sewerage Revenue Bonds Series 2004 Fund