## Sheet1
NO. | Report of Accomplishments | STATUS OF PROJECT OR ACTIVITY |  |  |  | **Currently underway or temporarily postponed activities or projects should appear in new STWP
| Project or Activity from Previous STWP | Completed | ** Currently Underway | ** Postponed * | Not Accomplished * | * Explanation for Postponed or Not Accomplished Project or Activity
ECONOMIC DEVELOPMENT
1. | Establish a Planning Advisory Committee comprised of City Officials to explore |  |  |  | X | In 2003, the City hired their first professional planner and in 2006, a second professional planning position
| a variety of planning related issues, including transportation, water and sewer, zoning, |  |  |  |  | was created and filled. Additionally, the City has two City Councilmembers who are the Chair and
| "smart growth," and economic development. |  |  |  |  | Co-Chair of the Planning & Zoning Committee, resp. The planners and the Planning & Zoning Committee work
2. | Continue working with the Cherokee County Water and Sewerage Authority regarding | X | X |  |  | closely and in conjunction with the citizen appointed Planning & Zoning Commission to achieve these
| the provision of sewer service. |  |  |  |  | objectives set forth in 2002, though a "Planning Advisory Committee" was not established.
3. | Continue working with Georgia DOT regarding traffic flow around the City and the most |  | X
feasible alternatives for truck routes.
4. | Develop design guidelines and public relations efforts to encourage a vibrant downtown area. | X
5. | Coordinate local economic development efforts with Cherokee County and area |  | X
municipalities to further smart growth initiatives.
6. | Review the Official Zoning Map and revise as necessary to facilitate "smart growth" and | X
economic development.
7. | Identify those areas that will enhance the City's tax base for future annexation (light | X
industrial vs. residential).
.
NATURAL AND HISTORIC RESOURCES
1. | Complete renovation and restoration of the historic Holly Springs Train Depot. | X
2. | Compile and publish history of Holly Springs. | X
3. | Implement UGA historic study by nominating properties to the National Register of Historic |  |  | X |  | The UGA Historic Resources Study has been implemented; however, due to staffing limitations
| Places. |  |  |  |  | and a lack of financial resources over the past several years, the HPC has not nominated
4. | Seek funding for improvement projects through programs such as TE, LDF, RAF, LWCF, | X | X |  |  | properties for national recognition. This activity has been forwarded to the 2007-2013 STWP.
and others as appropriate.
5. | Prepare GIS Maps and databases for environmentally sensitive areas such as floodplains, |  | X
wetlands, groundwater, recharge areas, water supply watersheds, and soils.
6. | Continue implementing existing subdivision regulations and development regulations to | X | X
ensure protection of environmentally sensitive areas and preservation of greenspace.
7. | Prepare groundwater recharge area protection ordinance and wetlands protection ordinance | X |  | X |  | The wetlands protection ordinance was completed; however, the groundwater recharge area protection
| per DNR/DCA requirements. |  |  |  |  | ordinance was not. The reason for this incompletion is unknown, but it will be forwarded to the new STWP.
8. | Acquire and develop land for future park, recreation, and open space uses. | X | X
9. | Encourage innovative land development practices. | X | X
COMMUNITY FACILITIES AND SERVICES
1. | Finalize negotiations with the CCWSA regarding sewer service. | X
2. | Continue to provide public safety services through added resources, personnel, equipment | X | X
and technology.
3. | Continue pursuing available public safety grants. | X | X
4. | Begin construction of new municipal facility [public safety building]. | X
5. | Complete new municipal facility [public safety building]. | X
6. | Provide adequate administrative and professional staff to meet existing and future needs | X | X
7. | Continue working with the Georgia DOT and other agencies regarding improvements to |  | X
Hickory Street, Holly Street, and proposed truck routes.
8. | Continue working cooperatively with area municipalities, Cherokee County, ARC, Georgia | X | X
DOT, and GRTA to coordinate transportation planning efforts
9. | Seek financial assistance for park and recreation improvements from state and federal | X
programs such as LDF, RAF, LWCF, and Georgia's new greenspace program.
HOUSING
1. | Continue active program of code enforcement. | X | X
2. | Review and amend the Zoning Ordinance and Official Zoning Map for use in guiding future | X
housing types and densities.
3. | Actively begin planning for the introduction of new public sewer service. |  |  |  | X | The City of Holly Springs Water System was purchased by the Cherokee County Water/Sewerage
Authority, subsequent to the adoption of this STWP. Along with the sale of the system, the City entered
| LAND USE |  |  |  |  | into a contract with CCWSA to provide water and sewer services for the entire City.
1. | Prepare GIS land use maps. | X
2. | Continue using the Comprehensive Plan in the review of rezoning requests. | X | X
3. | Encourage planned, mixed-use development that does not detract from established | X | X
residential areas.
4. | Encourage the rezoning of property within the downtown area from Industrial to |  | X
Commercial.
5. | Protect stable residential areas from encroachment by incompatible land uses. | X | X
6. | Use the provision of public sewer service to direct the location of high density residential | X | X
development.
7. | Participate in and support cooperative efforts between Cherokee County and its | X | X
municipalities regarding land use and zoning issues.
8. | Use the Comprehensive Plan and Future Land Use Element as a guide when reviewing | X | X
and deciding on rezoning requests.
9. | Establish administrative procedures that require written staff reports be prepared and | X
submitted to the Planning & Zoning Board and City Council for all rezoning requests.
10. | Continue using the services of AICP-certified planning professionals | X | X
11. | Adopt and implement design guidelines for the Technology Ridge Corridor |  |  |  | X | The City opted not to participate in this I-575 overlay district, originally developed by Cherokee County.
GENERAL
1. | Prepare new Comprehensive Plan |  | X
2. | Review the Comprehensive Plan for consistency with the ARC's RDP. | X