## RLI Orientation
Time | Unit | Lead | Support | Process | Materials | Notes
| Submit posters to be printed to Barry | Sade |  | email barry the docs for posters
| Pick up posters from boards from Barry | Robert
2018-09-10 | tape posters to boards | Robert
| Check-in evoluation/John Hammond | Sade
2018-09-10 | Send email reminder to participants | Sade
2:00-2:30 | Pulling supplies | Holly |  | pull out supplies for Orientation Event | (5 )poster boards. (5) posters to include map of region, collage of images, and 3 boards, post-it notes (15), markers (40), pens (40), name tags, easels (6), stickers 80
2018-09-13
| Vases | Stephen |  | Bring vases to Wrecking Bar | 4 small vases for high tops/ 30 in and 3 larger vases for bigger tables 48in
12:00-1:00p.m. | Floral arrangments | Sade |  | Pick-up flowers from Trader Joes and create floral arrangments
2:30-3:30 | Packing Vehicles/ Event Supplies | Josh | Robert | Pack the PA system. Bring poster boards, name-tag, easels, pens, markers, post-its. See above materials for full list | poster boards and posters, post-it notes, markers (40), pens (40)
Arrival 3:30pm
3:30 | Set-up begins | Maraina Staff |  | Tables are set and arraganged at this time. Food is bought in
3:30 | Check-in with Staff | Sade | Team | Make introductions. Overview of the evevning and points of contact for different needs
3:45 | Review Program and walk-thru program flow | Sade
3:30-4:00 | Set up AV and check | Robert | Josh | Make sure that the AV is set and check sound
3:30-3:45 | Placing floral arrangements on tables | Ashley |  |  |  | The timing depends on the how fast the tables are set up by Mariana staff
3:30-4:00 | Setting up easels, markers, supplies | Stephen, Josh
3:30-4:00 | Coordinate with caterers | Sade |  | Review how the food will come out and stations will be set up |  | We have a $600 bar limit. Then we will begin a tab. If someone asks about the tab ask them to see Stephen or I
4:30 | Evolution jazz band arrives | Robert | Josh | Coordinate with Jazz band and assistant in any set up | They will bring all the music and AV needs they require. | Just make sure to look out for them. One person should be in the parking lot to make sure they know what entrance to come in.
4:45 | Coorinating with valet | Josh |  | Have a conversation and make sure that things go smoothly. Check with him occassionally throughout the evening.
4:45-6:0 | Stand near door to welcome people in | Ashley |  | welcome people encourage them put their |  | Remind them of the activities in the other room. We will be taking this information with us to Savannah
5:15-5:20 | Program begins | Introductions | Stpehen Causby
5:20-5:30 | RLI Welcome | Sade
5:20-5:30 | RLI Staff Introductions | Sade |  |  |  | everyone should be in the room, so that they can be introduced and after please follow planning guide

## RLI Packing
Time | Unit | Lead | Support | Process | Materials | Notes

## RLI Week
Time | Unit | Lead | Support | Process | Materials | Notes